## Consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - FOR SUBMISSION TO PPDA & MoFPED
PROCURING & DISPOSAL UNIT: MINISTRY OF WATER AND ENVIRONMENT
Financial Year 2019/20
S/No | Dept | Subject of Procurement | Plan | Currency | Estimated Cost | Source of Funding | Procurement Method |  | Request for Expression of Interest |  |  |  | Invitation of proposals and approval for award |  |  |  |  | Completion Date
|  |  | vs. |  |  |  |  | Contract Type | Invitation of proposals date | Closing-Opening | Approval of Shortlist | Notification Date | Invitation of proposals Date | Submission/ Opening Date | Approval of final Evaluation Report | Notification Date | Contract Signing Date
Actual
1 | WRPRD | Preparation of 4 Catchment Management Plans in: Lot 1 Nyamugasani & Kafu in Albert WMZ and Lot 2: Sezibwa & Okweng in Kyoga WMZ. | Plan | USD | 5700000 | World Bank/ GOU | Shortlist with publication | Lumpsum | 2019-08-13 | 2019-09-05 | 2019-09-05 | 2019-09-08 | 2019-09-18 | 2019-10-11 | 2019-12-10 | 2019-12-15 | 2020-01-14
Actual
2 | WRPRD | Preparation of Albert WMZ Water Resources Strategy and Action Plan | Plan | USD | 1500000 | World Bank/ GOU | Shortlist with publication | Lumpsum | 2019-10-15 | 2019-11-07 | 2019-11-27 | 2019-10-16 | 2019-11-08 | 2019-11-28 | 2019-10-17 | 2019-11-09 | 2019-11-29
Actual
3 | WRPRD | Implementation of priority WRM measures in: Lot 1: Lwakhakha sub-catchment Lot 2: Aswa II sub-catchment Lot 3: Kochi sub-catchment Lot 4: Middle Awoja sub-catchment | Plan | USD | 9094000 | World Bank/ GOU | Shortlist with publication | Lumpsum | 2019-10-18 | 2019-11-10 | 2019-12-03 | 2019-12-26 | 2020-01-18 | 2020-02-10 | 2020-03-04 | 2020-03-27 | 2020-04-19
Actual
4 | WRPRD | Consultancy Services for quantification of the available groundwater and assessment of sustainability of groundwater development | Plan | USD | 2000000 | World Bank/ GOU | Shortlist with publication | Lumpsum | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22 | 2020-01-11 | 31-January-20
Actual
5 | WRPRD | Roll out of Water Information System in Victoria, Upper Nile, Albertine and Kyoga WMZ | Plan | USD | 3400000 | World Bank/ GOU | Shortlist with publication | Lumpsum | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22 | 2020-01-11 | 2020-01-31
Actual
6 | WRPRD | Consultancy Services for Quality Assurance of the roll out of Water Information System in Victoria, Upper Nile, Albertine and Kyoga WMZ | Plan | USD | 400000 | World Bank/ GOU | Shortlist with publication | Lumpsum | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22 | 2020-01-11 | 2020-01-31
Actual
7 | WRPRD | Preparation of 6 micro Catchment Management Plans in: Lot 1-Ora; Lot 2 – Laropi; Lot 3 – Ayugi; Lot 4- Anyau; Lot 5-Kaya | Plan | USD | 880000 | World Bank/ GOU | Shortlist with publication | Lumpsum | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22 | 2020-01-11 | 2020-01-31
Actual
8 | WRPRD | Consultancy to Develop a Communication plan | Plan | USD | 15000 | Adaptation Fund | Shortlist with publication | Lumpsum | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22 | 2020-01-11 | 2020-01-31
Actual
9 | WRPRD/WMZ | Consultancy Services- short term | Plan | UGX | 235000000 | GOU | Shortlist with publication | Lumpsum | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22 | 2020-01-11 | 2020-01-31
Actual
10 | RWSSD | Consultancy services for feasibility study and detailed engineering design of 5 piped water systems in WestNile region, Moroto, Kabarole, Kween and Kasese districts | Plan | UGX | 3000000000 | GoU | Shortlist with publication | Lumpsum | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27 | 2020-07-27 | 2020-08-26
Actual
11 | RWSSD | Consultancy Services for community mobilisation and sanitation/hygiene promotion activities of water supply and sanitation systems in the Integrated Water Management and Development Project (IWMDP) | Plan | UGX | 2000000000 | GoU/Donor | Shortlist with publication | Lumpsum | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27 | 2020-07-27 | 2020-08-26
Actual
12 | RWSSD | Consultancy services for Environmental and Social Impact Assessments for water supply systems in rural areas. | Plan | UGX | 250000000 | GoU/Donor | Shortlist with publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
13 | RWSSD | Consultancy Services for Resettlement Action Plan for water supply systems in rural areas | Plan | UGX | 250000000 | GoU/Donor | Shortlist with publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
14 | RWSSD | Consultancy services for design review and construction supervision of water and sanitation infrastructructure under different construction contracts | Plan | UGX | 4500000000 | GoU/Donor | Shortlist with publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
15 | RWSSD | Consultancy services for Benchmarking and documenting the Support to Rural Water Project (Videography) | Plan | UGX | 50000000 | GoU | Shortlist without Publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
16 | RWSSD | Consultancy services for Evaluation of Support to Rural Water Project (End of Project) | Plan | UGX | 300000000 | GoU | Shortlist with publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
17 | RWSSD | Consultancy services for an update on the Rural water database, capacity building and traininig of District Local Governments and Regional Offices | Plan | UGX | 100000000 | GoU/Donor | Shortlist without Publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
18 | RWSSD | Community planning, mobilisation and advocacy in programme districts (including launch activities) | Plan | UGX | 150000000 | GoU | Shortlist without Publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
19 | WURD | Consultancy services to carry out Management Audits conducted on NWSC and small towns. | Plan | UGX | 197237000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
20 | WURD | Consultancy services on tariff review and update of Tariff policy | Plan | UGX | 750000000 | ADB | Shortlist with publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
21 | WURD | Consultancy services on developing regulatory tools | Plan | UGX | 2227000000 | ADB | Shortlist with publication | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20 | 2019-11-09 | 2019-11-29 | 2019-12-19 | 2020-01-08
Actual
22 | WURD | Consultancy services to carry out Study on affordability and willingness to pay. | Plan | UGX | 198000000 | GoU | Shortlist without Publication | Lumpsum | 2019-07-01 | 2019-07-11 | 2019-07-21 | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09 | 2019-09-19
Actual
23 | WURD | Consultancy services for Strengthening Regional Regulation Units | Plan | UGX | 592000000 | World Bank | Shortlist with publication | Lumpsum | 2019-07-01 | 2019-07-11 | 2019-07-21 | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09 | 2019-09-19
Actual
24 | WURD | Consultancy services in branding services to improve on the branding of MWE | Plan | UGX | 190000000 | GoU | Shortlist with publication | 2019-07-11 | 2019-07-21 | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09 | 2019-09-19 | 2019-09-09 | 2019-09-19
Actual
25 | WURD | Consultancy services for Social media boost, advertising, design production | Plan | UGX | 180000000 | GoU | Shortlist with publication | Lumpsum | 2019-09-01 | 2019-10-01 | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28
Actual
26 | WURD | Consultancy services for marketing of Water and Environment activities | Plan | UGX | 200000000 | GoU | Shortlist without Publication | Lumpsum | 2019-09-01 | 2019-10-01 | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28
Actual
27 | F&A | Long term consultancy | Plan | UGX | 100000000 | GoU | Shortlist without Publication | Lumpsum | 2019-09-01 | 2019-10-01 | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28
Actual
28 | WQM/IMBCP | Procure supervising consultant and Contractor for laboratory block in Entebbe | Plan | UGX | 50000000 | GoU | Shortlist without Publication | Lumpsum | 2019-09-01 | 2019-10-01 | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28
Actual
29 | WQM/IMBCP | Procure a consultant to undertake feasibility studies for restoration activities in the IMB | Plan | UGX | 25000000 | GoU | Shortlist without Publication | Lumpsum | 2019-09-01 | 2019-10-01 | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28
Actual
30 | WQM/IMBCP | Procure consultancy for laboratory accreditation | Plan | UGX | 446000000 | GoU | Shortlist with publication | Lumpsum | 2019-09-01 | 2019-10-01 | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28
Plan
Actual
31 | FIEFOC II | Consultancy services for training farmers on agronomy, soil and land improvement practices Lot 2: Tochi Irrigation Scheme (retendered) | Plan | UGX | 1200000000 | Donor | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
32 | FIEFOC II | Consultancy Services to conduct capacity building activities in Post harvest handling, food processing technologies and practices for agricultural products in watershed areas of Lot 1: Wadelai and Tochi; Lot 2: Mubuku II, Doho II and Ngenge Irigation schemes | Plan | UGX | 2394130000 | Donor | Shortlist with publication |  | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
33 | FIEFOC II | Consultancy Services to Empower farmers and farmer groups in agribusiness skills, commodity bulking and collective marketing, | Plan | UGX | 1600000000 |  | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
34 | FIEFOC II | Consultancy Services to train farmers and farmer groups in financial accessibility | Plan | UGX | 900000000 | Donor | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
35 | FIEFOC II | Consultancy services to Conduct community sensitisations on energy conservation technologies ( Includes procurement of Energy Saving stoves and others) | Plan | UGX | 971650000 | Donor | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
36 | FIEFOC II | Consultancy services for Forest Resources Assessment outside protected areas to establish 10 sets of private natural forests, community forests in selected hot spots in the catchment areas of the 5 schemes. | Plan | UGX | 730000000 | Donor | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
37 | FIEFOC II | Consultancy services for Training and technical support to GIS (Develop data base and training on GIS Applications) | Plan | UGX | 663000000 | Donor | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
38 | WMD | Procure consultancy to conduct feasibility studies on ENR | Plan | UGX | 100000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
39 | WMD | Procure consultancy to link NWIS to DLG Systems | Plan | UGX | 200000000 | GOU | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
40 | WSDF-C | Individual Consultancies for feasibility study for water supply systems for selected towns | Plan | UGX | 420000000 | GOU | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
41 | WSDF-C | Hydrogeological investigations and drilling and test pumping supervision | Plan | UGX | 350000000 | GOU | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
42 | WSDF-C | Consultancy services for corporateimage and identity management under framework contract. | Plan | UGX | 200000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
43 | WSDF-C | Consultancy Services for location, topographic, cadastral and valuation survey in WSDF-C areas | Plan | UGX | 420000000 | GOU | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
44 | WSDF-C | Consultancy Services for production of drama shows in WSDF-C area of operation | Plan | UGX | 340000000 | GOU | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
45 | WSDF-C | Consultancy to undertake periodic Monitoring and Evaluation reviews with stakeholders, tracking and documenting progress on indicators and assessment of economic impact in 25No towns. | Plan | UGX | 450000000 | GOU | Shortlist with publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
46 | WSDF-C | Consultancy Services to Upgrade MIS Database to match present Planning, Budgeting requirement; Financial administration and Management; Contract and Performance Management of Consultants and Reporting | Plan | UGX | 115000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
47 | WSDF-C | Consultancy Services to undertake economic impact evaluation of WSSP I | Plan | UGX | 2100000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
48 | WSDF-C | Consulatncy Services to undertake Mobilisation and household surveys | Plan | UGX | 500000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
49 | ATC- RWSSD | Stakeholders engagement on Point of Use water treatment promotion (Consultancy services) | Plan | UGX | 30000000 |  | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
50 | ATC- RWSSD | 5 year development strategy (consultancy) | Plan | UGX | 30000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
51 | ATC- RWSSD | Development of manuals and guidelines for appropriate technologies (consultancy) | Plan | UGX | 100000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
52 | FSSD | Procurement of GIS Capacity building and re-tooling consultant | Plan | UGX | 683000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
53 | FSSD | Procurement of Forestry Assessment consultant | Plan | UGX | 740000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
54 | FSSD | Procurement of consultant on energy conservation Technologies | Plan | UGX | 360000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
55 | FSSD | Consumables (cleaning materials) | Plan | UGX | 12000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
56 | FSSD | Recruitment of Forest Officers | Plan | UGX | 52800000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
57 | FSSD | Recruitment of IT Specialist/GIS | Plan | UGX | 26400000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
58 | FSSD | Recruitment of Statistician | Plan | UGX | 26400000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
59 | FSSD | Vehicle service and maintenance | Plan | UGX | 35000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
60 | FSSD | Vehicle tyres | Plan | UGX | 25000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
61 | FSSD | Procurement of consultant to Review Forest Policy of 2001 and National Forestry and Tree Planting Act of 2003 | Plan | UGX | 350000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
62 | UWSSD | Consultancy Services for the design and re-design of piped water supply and sanitation systems in Small Towns (STs) and Rural Growth Centres (RGCs) under the Regional Umbrellas of Water and Sanitation Authorities | Plan | UGX | 1550000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
63 | UWSSD | Consultancy Services for Revision of the UWSSD M&E System, M&E Policy, M&E Manual, Project / Program Specific Data Management System and Operationalization of the Revised Indicators including establishment of the respective baseline Data | Plan | UGX | 190000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
64 | UWSSD | Procurement for market research and customer surveys about consumption patterns, and attitude, market trends and incomes of consumers and develop mechanisms for service delivery improvement. | Plan | UGX | 350000000 | GOU | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
65 | UWSSD | Consultancy to develop and implement business/commercial led strategies in customer care management/business management ethics to enable Umbrella of water and sanitation authorities achieve and maintain business viable fit between management, customers and other stakeholders. | Plan | UGX | 250000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
66 | UWSSD | Consultancy Services for the development of Guidelines and Operations Manual for Umbrellas of water and Sanitation Authorities (second edition - including management responsibility) | Plan | UGX | 450000000 | DONOR | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
67 | UWSSD | Consultancy services for strengthening community planning, mobilization and management arrangements in small towns water supply systems; lot 1 - Kyenjojo-Katoke, Bundibugyo Towns, lot 2 - Nakasongola, Dokolo, Kapchorwa Towns and lot 3 - Kayunga-Busana, Buikwe, Kamuli Towns | Plan | UGX | 3100000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
68 | UWSSD | Procurement of consultancy services to conduct studies and assessments to establish the national requirements for sewered and non - sewered sanitation services in Uganda | Plan | UGX | 9000000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
69 | UWSSD | Procurement of consultancy services to conduct feasibility studies and designs for sewered and/or non-sewered sewage treatment systems for Towns of Kalangala, Kayunga, Kagadi, Kiboga, Lyantonde and Kibaale | Plan | UGX | 5000000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
70 | UWSSD | Consultancy services for strengthening community planning, mobilization, sensitization and capacity building for; lot 1 - Nakasongola, Dokolo, Kayunga-Busana Town Water supply and Sanitation Systems | Plan | UGX | 3400000000 |  | Shortlist with Publication | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
71 | UWSSD | Consultancy services for feasibility designs for pilot projects under the Uganda strategic program for climate change resilience in Upper nile and Kyoga catchments | Plan | UGX | 7890000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
72 | UWSSD | Consultancy services for review and update of water and sanitation services tariff policy | plan | UGX | 836000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
73 | UWSSD | Consultancy services to develop water services technical and commercial regulatory tools | plan | UGX | 2516000000
Actual
74 | UWSSD | Consultancy services for economic empowerment through skills development for women and youth in Water, Sanitation and Environment activities | Plan | UGX | 1700000000 |  | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
75 | UWSSD | Consultancy services for Development of national strategy and implementation framework for bulk water supply | Plan | UGX | 1643000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
76 |  |  | Actual
77 | UWSSD | Consultancy services for update to Water and Sanitation atlas | Plan | UGX | 1133000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
78 | UWSSD | Consultancy services to strengthen Water and Environment Coordination and Monitoring and Evaluation framework | Plan | UGX | 1190000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
79 | UWSSD | Consultancy services to conduct feasibility studies in 10 No. strategic towns in various parts of Uganda | Plan | UGX | 6353760000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
80 | UWSSD | Consultancy services to conduct catchment protection, including training of women and youth groups and monitoring of ESMP implementation under STWSSP Lot 1 - Kyenjojo-Katoke, Bundibugyo; Lot 2 - Kayunga-Busana, Nakasongola, Dokolo and Lot 3 - Buikwe, Kamuli and Kapchorwa | Plan | UGX | 2395558550 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
81 | UWSSD | Consultancy services to conduct feasibility study, detailed design and construction supervision of faecal sludge management facilities in Dokolo, Buikwe and Kyenjojo-Katooke | Plan | UGX | 2728000000 |  | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
82 | UWSSD | Consultancy Services for Construction Supervision of Water Supply and Sanitation Systems in Busia Municipality and faecal sludge Sanitation/Facilities System, Source Protection Measures and Sanitation Facilities in Kumi-Nyero-Ngora | Plan | UGX | 1813000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
83 | UWSSD | Consultancy Services for Construction Supervision of Water Supply and Sanitation Systems in (a) Namasale and Sanitation Facilities in koboko (b)Kaliro-Namungalwe and (c) Sanitation Facilities in Rukungiri | Plan | UGX | 1846125000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
84 | UWSSD | Consultancy Services for Feasibility Study, Detailed Engineering Design and Construction Supervision of Water Supply and Sanitation System in Kyegegwa-Mpara-Ruyonza | Plan | UGX | 2399962500 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
85 | UWSSD | Feasibility Study, Detailed Engineering Design and Construction Supervision of Solar Powered Piped Water Supply Systems and Sanitation Facilities in Refugee Settlements and Host Districts of: Lot 1: Arua & Moyo, Lot 2: Yumbe, Lot 3: Adjumani & Lamwo | Plan | UGX | 7779570750 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
86 | UWSSD | Consultancy Services for the Professionalization of Umbrellas of Water and Sanitation | Plan | UGX | 2682500000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
actual
87 | UWSSD | Consultancy Services To Develop Town Sanitation Plans for Towns Of Kumi, Ngora, Nyero, Rukungiri, Koboko, Namungalwe, Kaliro, Namasale, Kyegegwa, Mpara, Ruyonza and Small Towns Of Busolwe, Kadama, Tirinyi, Kibuku, Butaleja, Budaka and a Sanitation Master Plan for Mbale Municipality | Plan | UGX | 4440000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
88 | UWSSD | Implementation of Developed towns Sanitation Plans | Plan | UGX | 4429620000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
89 | UWSSD | Consultancy Services to Conduct Community Engagement, Sanitation and Hygiene Promotion, Training on Operation and Maintenance of Sanitation Facilities in Towns of Busia, Kumi, Ngora, Nyero, Rukungiri, Koboko, Namungalwe, Kaliro, Namasale, Kyegegwa, Mpara, Ruyonza and Small Towns of Busolwe, Kadama, Tirinyi, Kibuku-Butaleja-Budaka Under IWMDP | Plan | UGX | 2960000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
90 | UWSSD | Consultancy Services for Feasibility Studies and Engineering Design of Piped Water Supply Systems in the Selected Towns of Oreta/Nyakwae (Abim), Losilang (Kotido) | Plan | UGX | 180000000 | DONOR | Shortlist without Publication | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
91 | UWSSD | Consultancy services for feasibility studies and Engineering Design of Piped Water Supply systems in Selected Towns of Kodike (Nakpak) and (Nabilatuk) | Plan | UGX | 180000000 | DONOR | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
92 | UWSSD | Consultancy services for Feasibility studies and Enginigeering Design of Piped Water Systems in 5 towns of; Lorengecora (Napak), Lorengea (Nakapiripirit), Karita (Amudat), Kalapata (Kaabong) and awac (Abim) | Plan | UGX | 360000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
93 | UWSSD | Consultancy services for Feasibility studies and Engineering Design of Piped Water Supply system in 5 Towns of; Amudat (Kaabong), Kapedo (Kaabong), Lokitalaebu (Kotido), Tokora (Nakapiripirit) | Plan | UGX | 250000000 | DONOR | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
94 | UWSSD | Sensitisation and Baseline Surveys | Plan | UGX | 150000000 |  | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
95 | UWSSD | Consultancy Services (Short Term) | Plan | UGX | 150000000 | DONOR | Shortlist without Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
96 | WSDF-N | Consultancy Services for Feasibiity Study, detailed design and construction supervision for piped water supply and sanitiation facilities for Amuru TC-Atiak RGC in Amuru district, Bibia/Elegu RGC in Amuru District | Plan | UGX | 1000000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
97 | WSDF-N | Consultancy Services for Detailed Designs of Water Supply Systems and sanitation Facillities of Aboke in Kole District, Ngai, Iceme and Otwal Railway Station in Oyam District. | Plan | UGX | 1000000000 | GOU
Actual
98 | WSDF-N | Consultancy Services for Feasibiity Study, detailed design and construction supervision for piped water supply and sanitiation facilities for odramachaku town in Arua district, Okokoro RGC in Maracha district and Keri-Oraba RGC in Koboko District | Plan | UGX | 1000000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actaual
98 | WSDF-N | Consultancy Services for Detailed Designs of Water Supply Systems and sanitation Facillities of of Bala and Kole RGCs in Kole District; Alebtong Town Council in Alebtong District and Apala RGC in Alebtong District | Plan | UGX | 1000000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
99 | WSDF-N | Consultancy services to design and produce IEC materials for sanitation and hand washing. | plan | UGX | 90000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27 | 2020-04-26
Actual
100 | WSDF-N | Consultancy services for detailed design of Feacal Sludge Management facility for cluster towns of Atiak, Bibia/Elegu, Pabbo, Parabong and Amuru TC in Amuru district | Plan | UGX | 150000000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actaul
101 | WSDF-N | Framework contract for drama groups | plan | UGX | 250000000 |  | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
actual
102 | WSDF-N | Consultancy Services to Develop an O&M Concept Paper for the Management of Water and Sanitation Facilities in Refugee Settlements | Plan | UGX | 50000000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
103 | WSDF-N | Consultancy Services to Develop a Concept Paper for Promoting Water for Production in Refugee Settlements | Plan | UGX | 50000000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
104 | WSDF-N | Procurement of Framework Contract for Geophysical Investigation and Construction Supervision of Production Wells in Selected RGCs in Northern Uganda. | Plan | UGX | 70000000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
105 | WSDF-N | Consultancy Services (Completion survey for 08towns under 2nd phase) | Plan | UGX | 350000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
106 | WSDF-N | Consultancy Services for capacity building of WSDF-N Engineering staff | plan | UGX | 50000000 | GOU
Actual
107 | WFPRC-N | Consultancy services for the design of 23 Small scale irrigation schemes in Upper Central, Northern and West Nile regions of Uganda | Plan | UGX | 1750000000 |  | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
108 | WFPRC-N | Consultancy services for design, production and dissemination of IEC materials for Water for Production materials | Plan | UGX | 250000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
109 | WFPRC-N | Consultancy services for establishment of sustainable management systems and implementation support for SSIS in Northern, Upper Central and West Nile Sub-regions | Plan | UGX | 150000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
110 | WFPRC-N | Consultancy services for Design of 4 valley tanks in Masindi, Maracha, Kiryandongo and Agago | Plan | UGX | 320000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
111 | WFPRC-N | Consultancy services for production of WfPRC-North Documentaries | Plan | UGX | 300000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
112 | WFPRC-N | Consultancy services for Hydro-geological services for Water for Production facilities | Plan | UGX | 600000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
113 | WFPRC-N | Consultancy services for Geotechnical services for Water for Production facilities | Plan | UGX | 600000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
114 | WFPRC-N | Consultancy services for Geotechnical services for Water for Production facilities | Plan | UGX | 600000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
115 | WFPRC-N | Services for operation, maintenance and management of Olweny irrigation scheme in Lira District | Plan | UGX | 400000000 | GOU | Shortlist with Publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27 | 2020-04-26
Actual
116 | UNWMZ | Consultancy Services to Carry out Capacity Building of Selected women Groups, Communities and Schools in Cook Stove Production, Woodlot Establishment, Business management and marketing in Aswa Catchment under Eureccca Project | Plan | UGX | 150000000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
117 | WSDF-E | Consultancy for Feasibility Studies and Designs for Mayuge area | Plan | UGX | 400000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
118 | WSDF-E | Consultancy for Feasibility Studies and Designs for Iganga-Idudi-Bugiri Area | Plan | UGX | 400000000 | GOU | Shortlist with Publication | Lumpsum
Actual
119 | WSDF-E | Consultancy for Feasibility Studies and Designs for Buyende Area | Plan | UGX | 400000000 |  | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
120 | WSDF-E | Consultancy for Media Services | Plan | UGX | 500000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
121 | WSDF-E | Consultancy Services for hydrological investigations, Siting, supervision of Drilling of (60) production Boreholes | Plan | UGX | 300000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
122 | WESLD | Consultancy to compile the SPR 2019 | Plan | UGX | 150000000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
123 | WESLD | Procurement of consultant for economic empowerment of women and youth | Plan | UGX | 1300000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
124 | WESLD | Procurement of consultant for dissemination of the revised water and sanitation gender strategy | Plan | UGX | 150000000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
125 | WESLD | Procurement of consultant for production of water and sanitation atlas | Plan | UGX | 800000000 | GOU | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
126 | WESLD | Consultancy to capacity build stakeholders in data management | Plan | UGX | 135000000 | GOU | Shortlist without Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
127 | REDD+ | Consultancy services to finalize and document Uganda's REDD+ Strategy | Plan | USD | 300000 | DONOR | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
128 | REDD+ | Technical advisor to support the design of two nationally acceptable, and internationally peer-reviewed Emissions Reductions Programs (ERPs) | Plan | USD | 54000 | DONOR | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
129 | REDD+ | Consultancy services to support implementation of Uganda REDD+ Gender strategy and Capacity building for IP organisations | Plan | USD | 100000 | DONOR | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
130 | REDD+ | Consultancy services to design and implement pilot Emissions Reduction Projects in two landscapes in Uganda | Plan | USD | 950000 | DONOR | Shortlist with Publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
131 | REDD+ | Communication/ Project Officer Uganda REDD+ Project | Plan | USD | 133000 | DONOR | SS | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
132 | REDD+ | Lead Technical Advisor to provide technical support to Ministry of Water and Environment on REDD+ readiness activities and elaboration of the project proposals under the FIP | Plan | USD | 222000 | DONOR | SS | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
133 | REDD+ | Development of the National Reference Scenario and Inventory of Forest Resources | plan | USD | 1479000 | DONOR | shortlist with publicaton of EOI | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
134 | REDD+ | Short term Consultancies | plan | UGX | 80000000 | GOU | Shortlist without publication | Lumpsum | 2019-08-16 | 2019-09-15 | 2019-10-15 | 2019-11-14 | 2019-12-14 | 2020-01-13 | 2020-02-12 | 2020-03-13 | 2020-04-12
Actual
135 | ITWAD | Procurement of Consultancy services for development of Nile Allocation tool | plan | UGX | 1000000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
136 | ITWAD | Procurement of consultancy services for the development of the Transboundary Strategy | Plan | UGX | 150000000 | GOU | Shortlist without publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
137 | ITWAD | Procurement of Consultancy services for the development of Transboundary database management system | Plan | UGX | 200000000 | GOU | Shortlist without publication | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
138 | ITWAD | Procurement of consultancy services for the identification of Transboundary Multipurpose Water Projects | Plan | UGX | 500000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 43887 | 43917
Actual
139 | ITWAD | Procurement of consultancy services for the development of Trans-boundary wetlands monographs and priority investment plans | Plan | UGX | 400000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-07-31 | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26
Actual
140 | ITWAD | Procurement of Consultancy services for Development of Kagera Catchment Management Plan between Uganda and Tanzania | Plan | UGX | 350000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-07-31 | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26
Actual
141 | CCD | Consultancy services (long-term) | Plan | UGX | 1500000000 | GOU-Donor | shortlist with publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27 | 2020-03-28
Actual
142 | LEAF 11 | Supervision and worthiness of the boats | Plan | UGX | 100760000 | Donor | LCS | Time base | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
143 | LEAF 11 | Development of pollution control plan | Plan | UGX | 74200000 | Donor | LCS | Time base | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
144 | LEAF 11 | Environmental and social mitigation measurres, Environmental capacity building, Environmental monitoring and control | Plan | UGX | 296800000 | Donor | LCS | Time base | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
145 | LEAF 11 | Construction Supervision of the surveillance station and research station | Plan | UGX | 400000000 | Donor | LCS | Time base | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
146 | LEAF 11 | Assessment of the status and functionality of gauging stations with the LEA Basin | Plan | UGX | 164000000 | Donor | LCS | Time base | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
147 | LEAF 11 | Implementation of catchment restoration initiatives | Plan | UGX | 2209000000 | Donor/GoU | LCS | Time base | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 43887 | 43917
Actual
148 | AWMZ | Semuliki CMC | Plan | UGX | 35000000 | GOU | Shortlist without publication | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17
Actual
149 | AWMZ | Mpanga CMC | Plan | UGX | 35000000 | GOU | Shortlist without publication | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17
Actual
150 | AWMZ | Wetland Protection | Plan | UGX | 400000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17
Actual
151 | AWMZ | Afforestation of Degraded Hotspots | Plan | UGX | 400000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 43908 | 43938
Actual
152 | AWMZ | River bank stabilization | Plan | UGX | 400000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 43908 | 43938
Actual
153 | AWMZ | Establishment of community nurseries | Plan | UGX | 400000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18 | 2020-04-17
Actual
154 | AWMZ | Kiiha CMC | Plan | UGX | 35000000 | GOU | Shortlist without publication | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 2020-03-18
Actual
155 | ITWAD | Consultancy services to development LVEMP III Environmental and Social Management Framework | Plan | UGX | 200000000 | GOU | Shortlist without publication | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19 | 2020-01-18 | 2020-02-17 | 43908 | 43938
Actual
156 | WfP | Consultancy Services for Formulation of a National Irrigation Master Plan for Uganda | Plan | UGX | 6600000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 22-7-19 | 2019-08-11 | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19 | 2019-12-09 | 2019-12-29
Actual
156 | WfP | Consultancy Services for the Development of the Water for Production Design Manual | Plan | UGX | 1500000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 22-7-19 | 2019-08-11 | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19 | 2019-12-09 | 2019-12-29
Actual
157 | WfP | Consultancy services for detailed design and supervision of Ojama dam and multi-purpose water systems and facilities in Serere District: | Plan | UGX | 1160026000 | GOU | shortlist with publicaton of EOI | Lumpsum | 22-7-19 | 2019-08-11 | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19 | 2019-12-09 | 2019-12-29
Actual
158 | WfP | Consultancy Services for Feasibility Studies and Preliminary Design of Multi-Purpose Storage Dams and Watering Facilities in Karamoja: Lot 1: Feasibility Studies and Preliminary Designs of Eight (8) Multi-Purpose Storage Dams and Watering Facilities in Moroto, Napak, Amudat and Nakapiripirit Districts | Plan | UGX | 1160026000 | GOU | shortlist with publicaton of EOI | Lumpsum | 22-7-19 | 2019-08-11 | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19 | 2019-12-09 | 2019-12-29
Actual
159 | WfP | Consultancy Services for Feasibility Studies and Preliminary Design of Multi-Purpose Storage Dams and Watering Facilities in Karamoja: Lot 2: Feasibility Studies and Preliminary Designs of Six (6) Multi-Purpose Storage Dams and Watering Facilities in Abim, Kotido and Kaaabong Districts | Plan | UGX | 899878000 | GOU | shortlist with publicaton of EOI | Lumpsum | 22-7-19 | 2019-08-11 | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19 | 2019-12-09 | 2019-12-29
Actual
160 | WfP | Consultancy Services for Designs for Rehabilitation of Lodoon dam in Napak District | Plan | UGX | 500000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 22-7-19 | 2019-08-11 | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19 | 2019-12-09 | 2019-12-29
Actual
161 | WfP | Consultancy Services for Feasibility Studies and Design of Mega irrigation schemes around Mt. Elgon area, Mt. Rwenzori, Agoro Hills and South-western Highlands:-Lot 1: Feasibility Studies for Mega irrigation schemes around Mt. Elgon area and Design of Amagoro irrigation scheme in Tororo District and Nabigaga in Kamuli District | Plan | UGX | 2985636367 | GOU | shortlist with publicaton of EOI | Lumpsum | 31-7-19 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19 | 2019-11-08 | 2019-11-28 | 2019-12-18 | 2020-01-07
Actual
162 | WfP | Consultancy Services for Feasibility Studies and Design of Mega irrigation schemes around Mt. Elgon area, Mt. Rwenzori, Agoro Hills and South-western Highlands:- Lot 2: Feasibility Studies for Mega irrigation schemes around Mt. Rwenzori area and Design of Rwimi irrigation scheme in Kabarole and Kasese Districts | Plan | UGX | 2999609600 | GOU | shortlist with publicaton of EOI | Lumpsum | 31-7-19 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19 | 2019-11-08 | 2019-11-28 | 2019-12-18 | 2020-01-07
Actual
165 | WfP | Consultancy Services for Feasibility Studies and Design of Mega irrigation schemes around Mt. Elgon area, Mt. Rwenzori, Agoro Hills and South-western Highlands:- Lot 3: Feasibility Studies for Mega irrigation schemes around Agoro Hills and Design of Nyimur, Purongo and Palyec irrigation schemes in Lamwo, Amuru and Nwoya District. | Plan | UGX | 3724757872 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
166 | WfP | Consultancy Services for Feasibility Studies and Detailed Designs of Medium and Large Irrigation Scale Schemes Covering Lot 1: Central Region | Plan | UGX | 2500000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
167 | WfP | Consultancy Services for Feasibility Studies and Detailed Designs of Medium and Large Irrigation Scale Schemes Covering Lot 2: The South Western Highlands | Plan | UGX | 3000000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
168 | WfP | Consultancy Services for Detailed Engineering Design of Unyama Namalu and Sipi irrigation schemes | Plan | UGX | 3168696000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
|  |  | Actual |  |  |  |  | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
169 | WfP | Consultancy services for design of Kagera corridor multi-purpose water for production infrastructure and facilities in Isingiro Districts | Plan | UGX | 1713109840 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
170 | WfP | Consultancy Services for Feasibility Studies and Design of Bulk water systems and Irrigation schemes: Lot 1: Lopei Bulk water systems and Irrigation scheme in Napak district | Plan | UGX | 1394451800 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
171 |  | Consultancy Services for Feasibility Studies and Design of Bulk water systems and Irrigation schemes: Lot 2: Lumbuye and Angololo Bulk water systems and Irrigation scheme in Luuka/Kaliro and Tororo districts respectively | Plan | UGX | 1600089440 | GOU | shortlist with publicaton of EOI |  | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
172 | WfP | Consultancy Services for Detailed design of Bulk Water Supply for Multi-Purpose uses for Kikatsi-Sanga-Kanyaryeru in Kiruhura District | Plan | UGX | 1463000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
173 | WfP | Procurement of Consultancy Services for pre-feasibility studies of Bulk Water Supply for Multi-Purpose uses for Nakasongola District | Plan | UGX | 200000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
174 | WfP | Consultancy services for Final Design for Kabuyanda Irrigation scheme in Isingiro District under World Bank funding | Plan | UGX | 1780395000 | WB/GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
175 | WfP | Consultancy services for Detailed Feasibility Studies and Design for Amagoro Irrigation Scheme in Tororo District under World Bank funding | Plan | UGX | 1900000000 | WB/GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
176 | WfP | Consultancy services for Detailed Feasibility Studies & Design of Matanda/Enengo Irrigation Scheme in Kanungu District under World Bank funding | Plan | UGX | 2000000000 | WB/GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
177 | WfP | Consultancy services for Environment and Social Impact Assessment (ESIA) and Resettlement Action Plans (RAP) for Irrigation Schemes of Rwimi, Kibimba, and Matanda. | Plan | UGX | 1033937216 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
178 | WfP | Consultancy services for Environment and Social Impact Assessment (ESIA) and Resettlement Action Plans (RAP) for Bulk Water Systems and irrigation schemes of, Lumbuye in Kaliro/Luka, Lopei in Napak and Angololo in Tororo. | Plan | UGX | 1031633396 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
179 | WfP | Consultancy services for Environment and Social Impact Assessment (ESIA) and Resettlement Action Plans (RAP) for Bulk Water Systems and irrigation schemes of Unyama in Amuru, Namalu in Nakapiripirit, Sipi in Bulambuli Districts and Kiruhura Bulk water system. | Plan | UGX | 1030016600 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
180 | WfP | Consultancy Services for Environment and Social Impact Assessment and Resettlement Action Plans (RAP) for Bulk Water Systems and irrigation schemes of Purongo in Nwoya, Palyec in Amuru, Nabigaga in Kamuli, Amagoro in Tororo and Kagera corridor in Isingiro Districts. | Plan | UGX | 1468464452 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
181 | WfP | Procurement of a Service Provider to Support protection Planning for storage reservoir Catchments of Andibo in Nebbi and Ongole dams in Katakwi Districts. | Plan | UGX | 250, 000,000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
182 | WfP | Procurement of Consultancy Services for Feasibility study for Katigondo Water for Production facility in Kalungu District | Plan | UGX | 500000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
183 | WfP | Consultancy Services for construction supervision of Rwengaaju model Village Irrigation Scheme in Kabarole District | Plan | UGX | 1500000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
184 | WfP | Consultancy services for Engineering services for strategic multi-purposes watering facilities | Plan | UGX | 3000000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
185 | WfP | Procurement of consultancy services for Solar powered pumping systems | Plan | UGX | 450000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 29-7-19 | 2019-08-28 | 2019-09-27 | 2019-10-27 | 2019-11-26 | 2019-12-26 | 2020-01-25 | 2020-02-24 | 2020-03-25
Actual
186 | WfP | Consultancy services for Baseline survey, annual update and Performance Evaluation of all WfP facilities in functionality Assessment Countrywide. | Plan | UGX | 600, 000,000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
187 | WfP | Consultancy Services for Pre-construction Implementation Support for Sustainable Management of Irrigation schemes and Bulk Water systems of; Lumbuye in Kaliro/Luuka Districts, Lopei in Napak District, Angololo in Tororo District, Sanga-Kikatsi-Kanyaryeru in Kiruhura District, Namatala in Mbale/Butaleja/Budaka and Kagera in Isingiro District. | Plan | UGX | 200000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
188 |  | Consultancy Services for Pre-construction Implementation Support for Sustainable Management of Irrigation schemes and Bulk Water systems of; Amagoro in Tororo District, Nyimur in Lamwo District, Kibimba in Gomba District, Purongo and Unyama in Amuru District and Namalu in Nakapiripirit District | Plan | UGX | 200000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
189 | WfP | Consultancy Services for Pre-construction Implementation Support for Sustainable Management for Irrigation schemes and watering facilities of; Water for Oil in Hoima/Kikube/Buliisa, Nabigaga in Kamuli District, Rwimi in Bunyangabu District, Palyec in Nwoya and Kabuyanda in Isingiro District. | Plan | UGX | 200000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
190 | WfP | Consultancy Services for Pre-construction Implementation Support for Sustainable Management of Irrigation schemes and watering systems of; Sipi in Bulambuli District and Matanda in Kanungu District | Plan | UGX | 200000000 | GOU | shortlist with publicaton of EOI |  | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
191 | WfP | Follow up Support for Sustainable Management of Irrigation Schemes of; Doho I in Butaleja District, Mubuku I in Kasese District and Agoro in Lamwo District and Rwengaaju Irrigation Scheme in Kabarole District | Plan | UGX | 3000000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
192 | WfP | Implementation Support for Sustainable Management, Functionality and Utilization of Water for Production storage through establishment of Farmer Field Schools (FFS) at WfP Old facilities | Plan | UGX | 500000000 | GOU | shortlist with publicaton of EOI | Lumpsum |  | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
193 | WfP | Design and construction supervision of Geregere earth dam and multipurpose water systems and facilities in Agago District | Plan | UGX | 983648000 | GOU | shortlist with publicaton of EOI | Lumpsum
Actual
194 | WfP | Design and construction supervision of Kyenshama earth dam and multipurpose water systems and facilities in Mbarara/Kiruhura District | Plan | UGX | 1044890000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
195 | WfP | Design and construction supervision of Makokwa and Kyahi earth dam and multipurpose water systems and facilities in Gomba District | Plan | UGX | 1341835525 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
196 |  | Design and construction supervision of Ojama earth dam and multipurpose water systems and facilities in Serere District | Plan | UGX | 1160026000 | GOU | shortlist with publicaton of EOI |  | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
197 | WfP | Consultancy Services for Detailed Design of Strategic Multi-Purpose Storage Dams, Irrigation Infrastructure and Watering Facilities of Kulodwongo in Abim, Kaputh (Panyangara) in Kotido, and Kokyeyo in Kaabong Districts. | Plan | UGX | 2500000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
198 | WfP | Consultancy Services for Detailed Design of Strategic Multi-Purpose Storage Dams, Irrigation Infrastructure and Watering Facilities of Korisae in Napak, Kokonyuko in Moroto, Kereswo in Amudat, Kanyangareng in Nakapiripirit and Komothing in Nabilatuk Districts. | Plan | UGX | 3500000000 | GoU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
198 | WfP | Procurement of Consultancy Services for Feasibility study for Katigondo Water for Production facility in Kalungu District | Plan | UGX | 500000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
199 | WfP | Consultancy Services for Project Planning, Design and Supervision under Drought Resilience in the Karamoja Sub-region project | Plan | UGX | 10000000000 | KFW/ GoU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
200 | WfP | Consultancy services for feasibility studies and design of earth dams and multipurpose water systems and facilities in Nakapiririt/ Amudat, Moroto and Kotido districts. | Plan | UGX | 10000000000 | KFW/ GoU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
201 | WfP | Consultancy Services for Pre-construction Implementation Support for Sustainable Management of earth dams and multipurpose water systems and facilities of; in Nakapiririt/ Amudat, Moroto and Kotido districts | Plan | UGX | 1000000000 | KFW/ GoU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
202 | WfP | Consultancy services for Baseline survey, and development of M&E system under Drought Resilience in the Karamoja Sub-region project. | Plan | UGX | 500, 000,000 | KFW/ GoU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
203 | WfP | Consultancy services for development of O&M concept under Drought Resilience in the Karamoja Sub-region project. | Plan | UGX | 500000000 | KFW/ GoU | shortlist with publicaton of EOI | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
204 | WfP | Consultancy Services for Preparation of Environment and Social Management Framework (ESMF) and Indigenous Peoples Planning Framework (IPPF) for the Drought Resilience Project in the Karamoja Sub-region. |  | UGX | 300000000 | KFW/ GoU | shortlist with publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27 | 2020-03-28
Actual
205 | WfP | Consultancy services for Environment and Social Impact Assessment (ESIA) and Resettlement Action Plans (RAP) for earth dams and multipurpose water systems and facilities in Nakapiririt/ Amudat, Moroto and Kotido districts under Drought Resilience in the Karamoja Sub-region project.. | Plan | UGX | 1500000000 | KFW/ GoU | ODB | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28 | 2020-03-29 | 2020-04-28 | 2020-05-28 | 2020-06-27
Actual
206 | HRM | Printing of the client's charter booklets | Plan | UGX | 48905100 | GOU | RFP | Lumpsum | 2019-07-01 | 2019-07-21 | 2019-08-10 | 2019-08-30 | 2019-09-19 | 2019-10-09 | 2019-10-29 | 2019-11-18 | 2019-12-08
Actual
207 | VWMZ | Consultancy services for detailed assessment of hotspots for intervention requirements and water source protection plans | Plan | UGX | 90000000 | GOU | Shorlist without publication | Time based/Lumpsum | 2018-06-21 | 13th-July-2018 | 27th-07-2018 | 27th-07-2018 | 27th-07-2018 | 27th-07-2018 | 02th-08-2019 | 30th-08-2019 | 13th-09-2019
Actual
208 | WSDF-SW | Consultancy services for Feasibility Studies and Detailed Designs for bulk water transfer for multipurpose use from L. Bunyonyi to Rubanda District | Plan | UGX | 700000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-08-08 | 2019-08-28 | 2019-09-17 | 2019-10-07 | 2019-10-27 | 2019-11-16 | 2019-12-06 | 2019-12-26 | 2020-01-15
Actual
209 | WSDF-SW | Hydrogeological Investigations and Drilling Supervision (48 No. Sites) | Plan | UGX | 252000000 | GOU | shortlist with publicaton of EOI | Framework | 2019-08-08 | 2019-08-28 | 2019-09-17 | 2019-10-07 | 2019-10-27 | 2019-11-16 | 2019-12-06 | 2019-12-26 | 2020-01-15
Actual
210 | WSDF-SW | Drama Shows (Luganda, Runyankitara and Rukonzo) | Plan | UGX | 305000000 | GOU | shortlist with publicaton of EOI | Framework | 2019-08-08 | 2019-08-28 | 2019-09-17 | 2019-10-07 | 2019-10-27 | 2019-11-16 | 2019-12-06 | 2019-12-26 | 2020-01-15
Actual
211 | WSDF-SW | Feasibility studies and detailed engineering designs of 24 Water supply and Sanitation System in South West Uganda | Plan | UGX | 1626000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-08-08 | 2019-08-28 | 2019-09-17 | 2019-10-07 | 2019-10-27 | 2019-11-16 | 2019-12-06 | 2019-12-26 | 2020-01-15
Actual
212 | WSDF-SW | Socio-Economic Survey | Plan | UGX | 50000000 | GOU | Shorlist without publication | Lumpsum | 2019-08-08 | 2019-08-28 | 2019-09-17 | 2019-10-07 | 2019-10-27 | 2019-11-16 | 2019-12-06 | 2019-12-26 | 2020-01-15
Actual
213 | WSDF-SW | Consultancy Services for Development and Implementation of Water source and catchment protection plans/measures, in Buyamba, Kambuga and Karago | Plan | UGX | 210000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-08-08 | 2019-08-28 | 2019-09-17 | 2019-10-07 | 2019-10-27 | 2019-11-16 | 2019-12-06 | 2019-12-26 | 2020-01-15
Actual
214 | WSDF-SW | Consultancy Services for Development and Implementation of Water source and catchment protection plans/measures, in Lwemiyaga, Kibugu, Igorora, Bethlehem-Nabigasa, Rushango, Nyakatonzi and Bigando Towns/RGCs | Plan | UGX | 420000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2019-08-08 | 2019-09-07 | 2019-10-07 | 2019-11-06 | 2019-12-06 | 2020-01-05 | 2020-02-04 | 2020-03-05 | 2020-04-04
Actual | bar: 2019-08-28
215 | WSDF-SW | Consultancy Services for Conducting of Environmental and Social Impact Assessment Studies, including monitoring of EMSP, for Kibugu, Igorora, Bethlehem-Nabigasa, Rushango, Nyakatonzi and Bigando Towns/RGCs | Plan | UGX | 180000000 | GOU | Shorlist without publication | Lumpsum | 2019-08-08 | 2019-09-07 | 2019-10-07 | 2019-11-06 | 2019-12-06 | 2020-01-05 | 2020-02-04 | 2020-03-05 | 2020-04-04
Actual
216 | WSDF-SW | Consultancy Services for Conducting of Sanitation, Hygiene and Environmental Surveys forKarago, Kibugu, Igorora, Bethlehem-Nabigasa, Rushango, Nyakatonzi and Bigando Towns/RGCs | Plan | UGX | 90000000 | GOU | Shorlist without publication | Lumpsum | 2019-08-08 | 2019-09-07 | 2019-10-07 | 2019-11-06 | 2019-12-06 | 2020-01-05 | 2020-02-04 | 2020-03-05 | 2020-04-04
Actual
217 | WSDF-SW | Procurement for Conducting end of implementation surveys on Sanitation, Hygiene and Environment for Karago, Kibugu, Igorora, Bethlehem-Nabigasa, Rushango, Nyakatonzi and Bigando Towns/RGCs | Plan | UGX | 90000000 | GOU | Shorlist without publication | Lumpsum | 2019-08-08 | 2019-09-07 | 2019-10-07 | 2019-11-06 | 2019-12-06 | 2020-01-05 | 2020-02-04 | 2020-03-05 | 2020-04-04
Actual
218 | WSDF-SW | Consultancy Services for Conducting end of implementation surveys on Sanitation, Hygiene and Environment for Kambuga, Lwemiyaga and Karago, Towns/RGCs | Plan | UGX | 45000000 | GOU | Shorlist without publication | Lumpsum | 2019-08-08 | 2019-09-07 | 2019-10-07 | 2019-11-06 | 2019-12-06 | 2020-01-05 | 2020-02-04 | 2020-03-05 | 2020-04-04
Actual
219 | WSDF-SW | Documentaries for Bethlehem, Nabigasa, Rushango & Kibugu | Plan | UGX | 90000000 | GOU | Shorlist without publication | Lumpsum | 2019-08-08 | 2019-09-07 | 2019-10-07 | 2019-11-06 | 2019-12-06 | 2020-01-05 | 2020-02-04
Actual
220 | WFPRC-SW | Implementation support for sustainable management of WfP facilities in western and lower central regions (training, capacity building, and formation of management committee for completed and on-going works) | Plan | UGX | 247000000 | GOU | shortlist with publicaton of EOI | Timebased | 2018-08-21 | 2018-09-20 | 2018-10-20 | 2018-11-19 | 2018-12-19 | 2019-01-18 | 2019-02-17 | 2019-03-19 | 2019-04-18
Actual
221 | WFPRC-SW | Documentary for selected Water for Production Facilities in the western and Lower Central regions | Plan | UGX | 90500000 | GOU | Shorlist without publication | Lumpsum | 2018-08-21 | 2018-09-20 | 2018-10-20 | 2018-11-19 | 2018-12-19 | 2019-01-18 | 2019-02-17 | 2019-03-19 | 2019-04-18
Actual
222 | WFPRC-SW | Consultancy Services for design of twenty five (25) small scale irrigation systems in western and lower central Uganda | Plan | UGX | 1100000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2018-08-21 | 2018-09-20 | 2018-10-20 | 2018-11-19 | 2018-12-19 | 2019-01-18 | 2019-02-17 | 2019-03-19 | 2019-04-18
Actual
223 | WFPRC-SW | Consultancy services for the design of Rushozi dams in Mbarara District | Plan | UGX | 350000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2018-08-21 | 2018-09-20 | 2018-10-20 | 2018-11-19 | 2018-12-19 | 2019-01-18 | 2019-02-17 | 2019-03-19 | 2019-04-18
Actual
224 | WFPRC-SW | Consultancy services for construction supervision of Kyenshama and Kyahi Dam in Mbarara and Gomba Districts | Plan | UGX | 400000000 | GOU | shortlist with publicaton of EOI | Lumpsum | 2018-08-21 | 2018-09-20 | 2018-10-20 | 2018-11-19 | 2018-12-19 | 2019-01-18 | 2019-02-17 | 2019-03-19 | 2019-04-18
Actual
225 | RWSSD | Consultancy Services for design, review and development of sector specific policies, guidelines and strategies for implementation of water and sanitation programmes countrywide | Plan | UGX | 20000000 | GOU | Shorlist without publication | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22
Actual
226 | PPD | Consultancy Services-for Project Impact Evaluation | Plan | UGX | 200000000 | GOU | Shorlist without publication | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22
Actual
227 | PPD | Consultancy Services-for development of Monitoring and Evaluation system | Plan | UGX | 190500000 | GOU | Shorlist without publication | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22
Actual
228 | PPD | Consultancy Services- For Preparation of Sector NDP III report | Plan | UGX | 160000000 | GOU | Shorlist without publication | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22
Actual
229 | PPD | Consultancy Services- Long-term - Training of of minstry staff on Intrgrated Bank of Projects | Plan | UGX | 35000000 | GOU | Shorlist without publication | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03 | 2019-10-23 | 2019-11-12 | 2019-12-02 | 2019-12-22
Actual
230 | WfP | Consultancy Services for Social Compliance Auditor for the Drought Resilience Project in the Karamoja Sub-region | Plan | UGX | 2500000000 | KFW/ GoU | shortlist with publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27 | 2020-03-28
Actual
231 | WfP | Consultancy Services for Management Consultant for the Drought Resilience Project in the Karamoja Sub-region | Plan | UGX | 2500000000 | KFW/ GoU | shortlist with publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
232 | WfP | Consultancy Services for Cadastral Survey and Titling of Irrigation Schemes of Lot 1: Rakai Bulk Water Scheme in Rakai District, Olweny Irrigation Scheme in Lira District and Rwengajju Irrigation Scheme in Kabarole District. | Plan | UGX | 200000000 | GOU | shortlist without publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
233 | WfP | Consultancy Services for Cadastral Survey and Titling of Irrigation Schemes of Lot 2: Mubuku II, Doho II and Ngenge Irrigation Schemes in Kasese, Butaleja and Kween Districts | Plan | UGX | 200000000 | GOU | shortlist without publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
234 | WfP | Consultancy Services for Cadastral Survey and Titling of Irrigation Schemes of Lot 3: Tochi, Wadelai and Agoro Irrigation Schemes in Oyam, Pakwach and Lamwo Districts. | Plan | UGX | 200000000 | GOU | shortlist without publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
235 | WfP | Individual Consultancy Services for Development of an Emergency Preparedness Plan (EPP) for Kabuyanda Irrigation Scheme in Isingiro District. | Plan | UGX | 50000000 | GOU | shortlist without publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
236 | WfP | Consultancy services for Environment and Social Impact Assessment (ESIA) and Resettlement Action Plans (RAP) for Nyimur Irrigation Scheme in Lamwo District. | Plan | UGX | 100000000 | GOU | shortlist without publicaton of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
237 | WfP | Consultancy Services for Feasibility Studies and Detailed Designs of Large Irrigation Scale Schemes in West Nile lowlands | Plan | UGX | 1500000000 | GOU | shortlist with publication of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
238 | WfP | Consultancy services for detailed design of Rushozi dam and multi-purpose water systems and facilities in Mbarara District | Plan | UGX | 1200000000 | GOU | shortlist with publication of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
239 | WfP | Consultancy Services for Conditional Assessment and Development of Rehabilitation, Operation and Maintenance Plan for Water for Production facilities in the Cattle Corridor Districts | Plan | UGX | 300000000 | GOU | shortlist with publication of EOI | Lumpsum | 2019-08-01 | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28 | 2020-02-27
Actual
|  | Prepared by |  |  | Name: |  |  |  | 2018-08-21: Approved by; 2018-09-20: Name:
[5 empty] | Signature: |  |  |  | 2018-09-20: Signature:
[5 empty] | Designation: |  |  |  | 2018-09-20: Designation:
[5 empty] | Date: |  |  |  | 2018-09-20: Date:
Formulas:
Closing-Opening = [Request for Expression of Interest]+23
Approval of Shortlist = [Closing-Opening]+M27
Approval of Shortlist = [Closing-Opening]+20
Notification Date = [Approval of Shortlist]+3
Notification Date = [Approval of final Evaluation Report]+5
Invitation of proposals Date = [Notification Date]+10
Submission/ Opening Date = [Invitation of proposals Date]+23
Approval of final Evaluation Report = [Submission/ Opening Date]+60
Contract Signing Date = [Notification Date]+30
Request for Expression of Interest = [Closing-Opening]-20

## Combined
MINISTRY OF WATER & ENVIRONMENT PROCUREMENT PLAN FY 2019-20
S/No |  | Subject of Procurement |  | Currency | Estimated Cost | Source of Funding | Procurement Method | Contract Type | INVITATION AND AWARD OF BIDS |  |  |  | Contract Signing Date
| Dept |  | Plan
|  |  | Actual | [5 empty] | Bid Invitation Date | Bid Closing-Opening | Approval Evaluation Report | Award Notification Date
1 | WRPRD | Construction of 12 monitoring stations (5No. Ground Water, 5No. Surface water, 2No. automatic weather stations). | Plan | USD | 391000 | World Bank | ODB
Actual
2 | WRPRD | Supply and Installation of: Lot 1: hydrometric equipment namely (5No. Ground Water, 5No. Surface water, 2No. automatic weather stations). Lot 2: Establishment of 3no. Automatic precipitation and 2no. dry deposition monitoring stations | Plan | USD | 1345000 | World Bank | ODB | Admeasuremet | 2020-01-01 | 2020-01-31 | 2020-03-01 | 2020-03-31
Actual
3 | WRPRD | Renovation and Expansion of the NWQRL at Entebbe | Plan | USD | 800000 | World Bank | ODB | Admeasuremet | 2020-01-01 | 2020-01-31 | 2020-03-01 | 2020-03-31
Actual
4 | WRPRD | Printing, Stationery, Photocopying and Binding | Plan | UGX | 16000000 | GOU | RFQ | lumpsum | 2020-01-01 | 2020-01-31 | 2020-03-01 | 2020-03-31
Actual
5 | WRPRD | Small Office Equipment | Plan | UGX | 10000000 | GOU | RFQ | lumpsum | 2020-01-01 | 2020-01-31 | 2020-03-01 | 2020-03-31
Actual
6 | WRPRD | Maintenance - Vehicles | Plan | UGX | 20000000 | GOU | RFQ | lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31
Actual
7 | WRPRD | Renovation of non-residential buildings | Plan | UGX | 100000000 | GOU | RFQ | Admeasuremet | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31
Actual
8 | WRPRD | Construction of various water harvesting structures | Plan | UGX | 100000000 | GOU | RFQ | Admeasuremet | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31
Actual
9 | WRPRD | Printing edited CMP Guidelines and Popular versions of the CMP Guidelines | Plan | USD | 21500 | Adaptation Fund/GOU | RDB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
10 | WRPRD | Printing services for Aswa, Awoja & Maziba CMPs incorporating climate change issues | Plan | USD | 21000 | Adaptation Fund/GOU | RDB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
11 | WRPRD | Procure hotel services (Workshop venue+meals) to disseminate CMP guidelines | Plan | USD | 48000 | Adaptation Fund | RDB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
12 | WRPRD | Procure and distribute seedlings to farmers | Plan | USD | 580000 | Adaptation Fund | ODB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
13 | WRPRD | Procurement of Inputs and implements for wetland restoration action plans | Plan | USD | 585000 | Adaptation Fund | ODB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
14 | WRPRD | Inputs and implements for river bank restoration action plans | Plan | USD | 390000 | Adaptation Fund | ODB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
15 | WRPRD | Inputs for water harvesting structures | Plan | USD | 504000 | Adaptation Fund | ODB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
actual
15 | WRPRD | Inputs for biophysical conservation structures | Plan | USD | 270000 | Adaptation Fund | ODB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
16 | WRPRD | Procure hotel services (Workshop venue+meals) to conduct workshops and meetings to sensitize on the revolving fund | Plan | USD | 270000 | Adaptation Fund | ODB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
17 | WRPRD | Renovation of buildings at various demonstration centres | Plan | USD | 390000 | Adaptation Fund | ODB | Lumpsum | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
18 | WRPRD | Set up demonstration plots /material | Plan | USD | 330000 | Adaptation Fund | ODB | Admeasuremet | 31-Aug-19 | 31-Aug-19 | 2019-09-20 | 2019-10-10 | 2019-10-30
Actual
19 | WRPRD | Maintenance – Vehicles | Plan | UGX | 50000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
20 | WRPRD | Computer supplies and Information Technology (IT) | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
21 | WRPRD | Printing, Stationery, Photocopying and Binding | Plan | UGX | 38000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
22 | WRPRD | Small Office Equipment | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
23 | WRPRD | Construction of non-residential buildings | Plan | UGX | 250000000 | GOU | RDB | Admeasurement | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
24 | WRPRD/WMZ | Computer supplies and Information Technology (IT) | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
25 | WRPRD/WMZ | Printing, Stationery, Photocopying and Binding | Plan | UGX | 40000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
26 | WRPRD/WMZ | Small Office Equipment | Plan | UGX | 15000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
27 | WRPRD/WMZ | Construction of various water harvesting structures | Plan | UGX | 1200000000 | GOU | ODB | Admeasurement | 2-Nov-19 | 2019-11-22 | 2019-12-12 | 2020-01-01 | 2020-01-21
Actual
28 | WRPRD/WMZ | Construction of non-residential buildings | Plan | UGX | 200000000 | GOU | ODB | Admeasurement | 2-Nov-19 | 2019-11-22 | 2019-12-12 | 2020-01-01 | 2020-01-21
Actual
29 | WRPRD/WMZ | Maintenance – Vehicles | Plan | UGX | 60000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
30 | RWSSD | Construction of Kanyabwanga Water Supply System in Mitooma district | Plan | UGX | 2320000000 | GOU/ AfDB | ODB | Admeasurement | 30-Sep-19 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28
Actual
31 | RWSSD | Construction of 40 solar powered mini piped water supply systems countrywide | Plan | UGX | 9000000000 | GOU/ AfDB | ODB | Admeasurement | 30-Sep-19 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28
Actual
32 | RWSSD | Construction of Highway Public Sanitation and Hygiene Facilities | Plan | UGX | 5000000000 | GoU | ODB | Admeasurement | 30-Sep-19 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28
Actual
33 | RWSSD | Rehabilitation of Nyakabingo Gravity Flow Scheme in Rukungiri district | Plan | UGX | 6000000000 | GoU | ODB | Admeasurement | 30-Sep-19 | 2019-10-30 | 2019-11-29 | 2019-12-29 | 2020-01-28
Actual
34 | RWSSD | Construction of Bitsya Water Supply and Sanitation System in Buhweju District | Plan | UGX | 10965000000 | GoU/Donor | ODB | Admeasurement | 2020-02-01 | 2020-03-02 | 2020-04-01 | 2020-05-01 | 2020-05-31
Actual
35 | RWSSD | Construction of Nyamugasani Gravity Flow Scheme in Kasese District | Plan | UGX | 8000000000 | GoU/Donor | ODB | Admeasurement | 2020-02-01 | 2020-03-02 | 2020-04-01 | 2020-05-01 | 2020-05-31
Actual
36 | RWSSD | Supply of office furniture and fittings for the Rural Water and Sanitation Department and Technical Support Units countrywide | Plan | UGX | 80000000 | GOU/JPF | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
37 | RWSSD | Supply of office cleaning materials and equipment | Plan | UGX | 54000000 | GoU/Donor | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
38 | RWSSD | Supply of community mobilisation materials, booklets, T-Shirts, banners and caps for promotion of water supply and sanitation improvement services | Plan | UGX | 65000000 | GoU/Donor | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
39 | RWSSD | Production of Information Education and Communication (IEC) materials for the Integrated Water Management and Development Project (IWMDP) | Plan | UGX | 150000000 | GoU/Donor | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
40 | RWSSD | Supply of Printers, photocopiers and accessories to the Rural Water and Sanitation Department | Plan | UGX | 40000000 | GoU/Donor | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
41 | RWSSD | Production of IEC materials for use in primary schools and public places for the climate change resilient programme in Budaka, Pallisa, Otuke, Katakwi and Bududa | Plan | UGX | 156000000 | GoU/AfDB | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
42 | RWSSD | Supply of Desktops and Laptops and computer accessories | Plan | UGX | 60000000 | GoU/Donor | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
43 | RWSSD | Repair of several vehicles in Rural water Department and TSUs | Plan | UGX | 410000000 | GOU/Donor | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
44 | RWSSD | Supply of vehicle tyres and accessories to rural water supply departmental vehicles | Plan | UGX | 100000000 | GOU/Donor | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
45 | RWSSD | Supply of assorted stationery and computer consumables | Plan | UGX | 55000000 | GoU/Donor | RFQ | Lumpsum | 2019-12-31 | 2020-01-20 | 2020-02-09 | 2020-02-29 | 2020-03-20
Actual
46 | RWSSD | Supply and installation of air conditioning and refrigeration systems. | Plan | UGX | 40000000 | GOU | RFQ | Lumpsum | 2020-01-30 | 2020-02-19 | 2020-03-10 | 2020-03-30 | 2020-04-19
Actual
47 | RWSSD | Supply of specialised equipment (GPSs, Hydrogeological survey equipment, Resistivity meters,borehole cameras etc,) to the Rural Water and Sanitation Department | Plan | UGX | 100000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
48 | RWSSD | Supply of pipes and fittings to water supplies in District Local Governments | Plan | UGX | 350000000 | GoU | RFQ | Lumpsum | 2020-01-30 | 2020-02-19 | 2020-03-10 | 2020-03-30 | 2020-04-19
Actual
49 | RWSSD | Non Consultancy Services for procurement of hotel services, venue, catering services for workshops, meetings and seminars | Plan | UGX | 300000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
50 | RWSSD | Non Consultancy Services for printing of Sector Guidelines to District Local Governments countrywide | Plan | UGX | 250000000 | GoU/Donor | RFQ | Lumpsum | 2020-01-30 | 2020-02-19 | 2020-03-10 | 2020-03-30 | 2020-04-19
Actual
51 | RWSSD | Non Consultancy Services for advertising bid opportunities and supplements in Newspapers and other media | Plan | UGX | 50000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
52 | WQM/IMBCP | Procure service provider for supply, installation, training and commissioning of water transport vessel | Plan | UGX | 67500000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
53 | WQM/IMBCP | Procure laboratory & office Furniture and fixtures | Plan | UGX | 10000000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
54 | WQM/IMBCP | Procure venue, accommodation, meals & catering services for meetings, workshops, retreats and seminars. | Plan | UGX | 50000000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
55 | WQM/IMBCP | Procure air tickets, travel documents & special hire services | Plan | UGX | 32000000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
56 | WQMD | Procure venue, accommodation, meals & catering services for meetings, workshops, retreats and seminars. | Plan | UGX | 10000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
57 | WQMD | Procure laboratory & office Furniture and fixtures | Plan | UGX | 5000000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
58 | WQMD | Procure services for minor repairs in the laboratory | Plan | UGX | 7500000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
59 | WQMD | Procure vehicle spares: Tyres, accessories & tools | Plan | UGX | 5000000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
60 | WQMD | Procure garage service for service & repairs of vehicles, generators and boats | Plan | UGX | 12500000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
61 | WQMD | Laboratory chemicals, reagents, glassware and assorted consumables/disposables | Plan | UGX | 20000000 | GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
62 | WURD | Supply of Motor Vehicles | plan | UGX | 420000000 | ADB | ODB | Lumpsum | 2019-12-12 | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01
Actual
63 | WURD | Supply and provision of equipment (drone camera etc) | Plan | UGX | 200000000 | GoU | RDB | Lumpsum | 2019-12-12 | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01
Actual
64 | WURD | Supply of vehicle tyres and accessories to rural water supply departmental vehicles | Plan | UGX | 100000000 | GOU/Donor | RFQ | Lumpsum | 2019-12-12 | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01
Actual
65 | WURD | Supply of assorted stationery, computer consumables and accessories | Plan | UGX | 55000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
66 | F&A | Computer Supplies | Plan | UGX | 106343244 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
67 | F&A | Meals and Teas | Plan | UGX | 58500000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
68 | F&A | Identity Cards | Plan | UGX | 4000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
69 | F&A | Assorted office stationery | Plan | UGX | 46000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
70 | F&A | small office equipment | Plan | UGX | 4000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
71 | F&A | corporate wear Uniform | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
72 | F&A | cleaning services | Plan | UGX | 15000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
73 | F&A | Vehicle Service and Repairs | Plan | UGX | 9000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
74 | WQM/IMBCP | Procure Books, Periodicals and Newspapers | Plan | UGX | 5000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
75 | WQM/IMBCP | Procure Computer Supplies and IT Services | Plan | UGX | 25000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
76 | WQM/IMBCP | Procure specialised goods and services (proficiency & accreditation services) | Plan | UGX | 10000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
77 | WQM/IMBCP | Procure small lab equipment & accessories, Laboratory chemicals, reagents, glassware and assorted consumables/disposables | Plan | UGX | 100000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
78 | WQM/IMBCP | Procure maintenance services for Machinery, Equipment and Furniture | Plan | UGX | 55000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
79 | UWSSD/ERT | Supply, Installation and Commissioning of Five (5No.) Solar Photovoltaic (PV) Energy Packages for Water Supply Schemes in Malere, Kyamutunzi, Kiboga, Kakooge and Katugo located in the Districts of Kamwenge, Kyenjojo, Kiboga and Nakasongola respectively | Plan | USD | 1500000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
80 | UWSSD/ERT | Supply, Installation and Commissioning of Six (6No.) Solar Photovoltaic (PV) Energy Packages for Water Supply Schemes in Wol, Oyam, Ovujyo, Kacheri, Awoo, and Aloi located in the Districts of Agago, Oyam, Maracha, Kotido, Omoro and Alebtong respectively | Plan | USD | 1500000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
81 | FIEFOC II | Variation to Construction of wadelai Irrigation scheme in Nebi District | Plan | UGX | 6542044000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
82 | FIEFOC II | Procurement of Excavators Lot 1: 2No Hydraulic Excavators; Lot 2: 5No Backhoe Excavators for the Irrigation schmes | Plan | UGX | 4500051000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
83 | FIEFOC II | Variation to Construction of Tochi Irrigation scheme in Oyam District | Plan | UGX | 4178780000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
84 | FIEFOC II | Variation to Construction of Doho Irrigation scheme in Butalejja District | Plan | UGX | 3751541000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
85 | FIEFOC II | Procurement of 5No Farm Tractors | Plan | UGX | 1000000000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
86 | FIEFOC II | Supply and Installation of 05 No. Meteological Stations for selected Irrigation Schemes | Plan | UGX | 645021000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
87 | FIEFOC II | Procurement of Tools and Implements for O&M of Irrigation Schemes | Plan | UGX | 637000000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
88 | FIEFOC II | Procurement of Specialised Eqipment:- Lot1 15No PAH Safe Fish Smoking Klins; Lot2 2000 No Bee Hives (of various types)and Accessories; Lot3 400 No sets of Honey Harvesting, Post Harvesting and Processing Equipments - smokers, protective gears etc; 20No Honey testing kits; 70No Honey processing equipment | Plan | UGX | 2000000000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
89 | FIEFOC II | Procurement of specialised Eqipment for Rice Harvesting:- 25No threshers and hand operated ripers(different types), 5No Power Tillers/tractors | Plan | UGX | 2000000000 | Donor | ICB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
90 | FIEFOC II | Procurement of inputs for fish demonstration in the 5 Irrigation Schemes | Plan | UGX | 330000000 | Donor | ODB | Lumpsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
91 | FIEFOC II | Construction of structures for silitation and soil erosion control and associated water points in the Irrigation Schemes | Plan | UGX | 3055608000 | Donor | ODB | Admeasurement | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
92 | FIEFOC II | Procurement of Tree seedlings for River bank and other Fragile Land Scapes Protection in 3 catchments of Wadelai, Tochi and Mubuku | Plan | UGX | 2050000000 | Donor | ODB | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
93 | FIEFOC II | Procurement of implements and specialised inputs for conservation farming and agroforestry (including Bio stoves for demonstration) | Plan | UGX | 2007500000 | Donor | ODB | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
94 | FIEFOC II | Procurement of Tree seedlings for River bank and other Fragile Land Scapes Protection in Lot 1: Doho Catchment; and Lot 2: Ngenge Catchment | Plan | UGX | 1400000000 | Donor | ODB | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
95 | FIEFOC II | Supply of IEC materials for INRM aspects | Plan | UGX | 200000000 | GOU | RDB | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
96 | FIEFOC II | Renovation of NPCU office premises | Plan | UGX | 200000000 | Donor | RDB | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
97 | FIEFOC II | Provision of Hotel and Catering Services | Plan | UGX | 95000000 |  | RFQ | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
98 | FIEFOC II | Supply of motor cycles for the 5 districts | Plan | UGX | 70800000 | Donor | RFQ | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
99 | FIEFOC II | Services for publication and advertsments | Plan | UGX | 50000000 | Donor | RFQ | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
100 | FIEFOC II | Service and Repair of Vehicles, equipment | Plan | UGX | 48000000 | Donor | RFQ | Lupsum | 2019-08-21 | 2019-09-20 | 2019-10-20 | 2019-11-19 | 2019-12-19
Actual
101 | FIEFOC II | Supply of stationery and office equipment | Plan | UGX | 46000000 | Donor | RFQ | Lupsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
102 | FIEFOC II | Supply of Tyres and rubes for project Motorcycles and vehicles | plan | UGX | 35000000 | Donor | RFQ | Lupsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
103 | FIEFOC II | Supply of Office furniture and fittings | Plan | UGX | 25000000 | Donor | RFQ | Lupsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
104 | FIEFOC II | Provision of secretarial services (Printing, Photocopying, Binding) | Plan | UGX | 25000000 | Donor | RFQ | Lupsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
105 | FIEFOC II | Supply of Communications Equipment (2No HD Camera, 1No Cam coder, 2No 50'' TV Sets and 1 set of IPAD) | Plan | UGX | 40000000 | Donor | RFQ | Lupsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
106 | FIEFOC II | Supply of Assorted IEC materials for FIEFOC 2 Project | Plan | UGX | 160000000 | Donor | RDB | Lupsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
107 | FIEFOC II | Services for production of comprehensive vidio documentary for FIEFOC 2 Project | Plan | UGX | 190000000 | Donor | RDB | Lupsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
108 | WMD | Procurement of Branded Pillars for the demarcation of critical Wetlands in Pallisa, Namutumba, Bukedea, Buhweju, Kanungu, Kamwenge, Kwania, Alebtong, Pader, Omoro, Nakapiririt, Kasanda, Mityana, Nakaseke, Kayunga and Masaka | Plan | UGX | 1000000000 | GOU | ODB | Lupsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
109 | WMD | water storage and detention facilities constructed in nyaruzinga and mpologoma wetland systems | Plan | UGX | 200000000 | GOU | RDB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
110 | WMD | Procurement of 1 single cabin pickups mounted with crew seat procured | Plan | UGX | 150000000 | GOU | ODB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
111 | WMD | Procurement of motorcycles | Plan | UGX | 200000000 | GOU | ODB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
112 | WMD | Procurement of Double cabin vechicle procured | Plan | UGX | 300000000 | GOU | ODB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
113 | WSDF-C | Construction of NgomaWater Supply System | Plan | UGX | 2500000000 | Donor | ODB | Admeasurement | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29
Actual
114 | WSDF-C | Drilling of Production Boreholes | Plan | UGX | 900000000 | GOU | ODB | Admeasurement | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29
Actual
| WSDF-C | Civil Works for Office Building Renovations | Plan | UGX | 165000000 | Gou | RDB | Admeasurement | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29
115 |  |  | Actual
116 | WSDF-C | Expansion and rehabilitation of 4 water supply systems | Plan | UGX | 2000000000 | GOU | ODB | Admeasurement | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29
Actual
117 | WSDF-C | Supply of Computers and IT Services | Plan | UGX | 100000000 | Donor/GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
118 | WSDF-C | Supply of Furniture and Fixtures | Plan | UGX | 270000000 | Donor/Gou | ODB | Lumpsum | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29
Actual
119 | WSDF-C | Supply of Small Office Equipment | Plan | UGX | 60000000 | Donor/Gou | RFQ | Lumpsum | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2
Actual
120 | WSDF-C | Supply of Good and Services | Plan | UGX | 100000000 | Donor/Gou | RFQ | Lumpsum | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2
Actual
121 | WSDF-C | Supply of Fuel, Oils and Lubricants | Plan | UGX | 340000000 | Donor/Gou | ODB | Lumpsum | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2
Actual
122 | WSDF-C | Supply of IEC Materials Under framework Contract | Plan | UGX | 500000000 | GOU | ODB | Lumpsum | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2
Actual
123 | WSDF-C | Provision of Visibility Items | Plan | UGX | 500000000 | Donor/GOU | ODB | Lumpsum | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2 | Q1-Q2
Actual
124 | WSDF-C | Supply of Pipes and Fittings Under Framework Contract | Plan | UGX | 1000000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
125 | WSDF-C | Supply of Stationery Under framework Contract | Plan | UGX | 120000000 | GOU | RDB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
126 | WSDF-C | Electricity | Plan | UGX | 32000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
127 | WSDF-C | Cleaning Services | Plan | UGX | 120000000 | GOU | RDB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
128 | WSDF-C | Water | Plan | UGX | 6000000 | GOU | DP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
129 | WSDF-C | Provision of Security Services | Plan | UGX | 32000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
130 | WSDF-C | Repair and Maintenance of Vehicles under framework contract | Plan | UGX | 240000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
131 | WSDF-C | Provision of Hotel Services | Plan | UGX | 230000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
132 | D/DWRM | Procure Books, Periodicals and Newspapers | Plan | UGX | 5000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
133 | D/DWRM | Procure Computer Supplies and IT Services | Plan | UGX | 7000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
134 | D/DWRM | Procure Computers, Laptops and associated Accessories | Plan | UGX | 15000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
135 | D/DWRM | Procure Printing, stationery and binding services | Plan | UGX | 25000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
136 | D/DWRM | Procure security services , guard protective clothing and uniforms | Plan | UGX | 14000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
137 | D/DWRM | Procure garage service for service & repairs of vehicles, generators and boats | Plan | UGX | 12500000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
138 | D/DWRM | Procure vehicle spares: Tyres, accessories & tools | Plan | UGX | 7000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
139 | D/DWRM | Procure office Furniture and fixtures | Plan | UGX | 1500000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
140 | D/DWRM | Procure venue, accommodation, meals & catering services for meetings, workshops, retreats and seminars. | Plan | UGX | 25000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
141 | D/DWD | Stationery and Photocopying | Plan | UGX | 10000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
142 | D/DWD | Computer suppies and IT | Plan | UGX | 14000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
143 | D/DWD | Small office equipment | Plan | UGX | 7500000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
144 | D/DWD | Vehicle Maintainance | Plan | UGX | 8000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
145 | ATC- RWSSD | Development of ground water recharge wells (Works) | Plan | UGX | 165000000 | GOU | RDB | Admeasurement | 1-10-19 | 2019-10-21 | 2019-11-10 | 2019-11-30 | 2019-12-20
Actual
146 | ATC- RWSSD | Installation of waste water recovery systems (Works) | Plan | UGX | 165000000 | GOU | RDB | Admeasurement | 1-10-19 | 2019-10-21 | 2019-11-10 | 2019-11-30 | 2019-12-20
Actual
147 | ATC- RWSSD | Supply and installation of Materials testing, calibration and quality assurance system (Works) | Plan | UGX | 70000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
148 | ATC- RWSSD | Supply of materials for MHM and liquid soap project | Plan | UGX | 25000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
149 | ATC- RWSSD | Purchase of a utility installed lab van | Plan | UGX | 250000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
150 | ATC- RWSSD | Supply and Installation of an advanced laboratory refrigerator | Plan | UGX | 30000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
Actual
151 | ATC- RWSSD | Supply of stationary and materials for office running | Plan | UGX | 6000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
152 | ATC- RWSSD | Building and demonstration of appropriate technologies (Works) | Plan | UGX | 100000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
153 | ATC- RWSSD | International WASH symposium | Plan | UGX | 50000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
154 | ATC- RWSSD | Development and printing of Quarterly newsletters and annual report | Plan | UGX | 10000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
155 | ATC- RWSSD | Designing and installation of Road signages and rebranding of ATC premises | Plan | UGX | 11540000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
156 | ATC- RWSSD | Supply and Installation of an automated solar powered prepaid water dispensing systems | Plan | UGX | 25500000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
157 | ATC- RWSSD | Supply of assorted bulky materials for production of sanitary pads | Plan | UGX | 21800000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
158 | ATC- RWSSD | Internet service provider and website hosting | Plan | UGX | 6000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
159 | ATC- RWSSD | Maintenance of generator | plan | UGX | 4000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
actaul
160 | FSSD | Newspaper Adverts and Articles | plan | UGX | 18000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
actaul
161 | FSSD | Printing and Stationary | plan | UGX | 20000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actaul
162 | FSSD | Procurement of Seedlings | plan | UGX | 1800000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
163 | FSSD | Procurement of Seedlings | plan | UGX | 4400000000 | GOU/DONOR | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
164 | FSSD | Procurement of Seedlings | plan | UGX | 2400000000 | REDD+/DONOR | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
165 | FSSD | Procurement of Seedlings | plan | UGX | 1400000000 | Donor | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
166 | FSSD | Procurement of Seedlings | plan | UGX | 4000000000 | GOU/DONOR | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
167 | FSSD | Procurement of Seedlings | Plan | UGX | 2050000000 | NDF | ODB | Lumpsum | 2020-04-01 | 2020-05-01 | 2020-05-31 | 2020-06-30 | 2020-07-30
Actual
168 | FSSD | Procurement of Seedlings | Plan | UGX | 880053000 | GOU/RWSSD | ODB | Lumpsum | 2020-04-01 | 2020-05-01 | 2020-05-31 | 2020-06-30 | 2020-07-30
Actual
169 | FSSD | Procurement of Seedlings | Plan | UGX | 355853547 | GOU/RWSSD | ODB | Lumpsum | 2020-04-01 | 2020-05-01 | 2020-05-31 | 2020-06-30 | 2020-07-30
Actual
| FSSD | Workshop materials and logistics | Plan | UGX | 100000000 | Donor | RFP | Lumpsum | 2020-04-01 | 2020-05-01 | 2020-05-31 | 2020-06-30 | 2020-07-30
170 |  |  | Actual
171 | FSSD | Workshop materials and logistics | Plan | UGX | 40000000 | Donor | RFP | Lumpsum | 2020-04-01 | 2020-05-01 | 2020-05-31 | 2020-06-30 | 2020-07-30
Actual
172 | FSSD | Recruitment of Sub County Forest Technical Officers (Service Providers) | Plan | UGX | 600000000 | FIEFOC GoU | ODB | Lumpsum | 2020-04-01 | 2020-05-01 | 2020-05-31 | 2020-06-30 | 2020-07-30
Actual
173 | FSSD | Recruitment of Communications/Information Officer | Plan | UGX | 26400000 | FIEFOC GoU | ODB | Lumpsum | 2020-04-01 | 2020-05-01 | 2020-05-31 | 2020-06-30 | 2020-07-30
Actual
174 | FSSD | Recruitment of GIS Specialist | Plan | UGX | 200000000 | Donor | ODB | Lumpsum | 2020-04-01 | 2020-05-01 | 2020-05-31 | 2020-06-30 | 2020-07-30
Actual
175 | FSSD | Procurement of Computer Supplies | Plan | UGX | 42000000 | Donor | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
176 | FSSD | Procurement of Office equipment and furniture (filling carbinnets, tables, chairs for centre and 4 regional offices ) | Plan | UGX | 30000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
177 | FSSD | Printing of Forest Produce Movement Permit books and Forest Produce Declaration Forms | plan | UGX | 20000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
178 | FSSD | Maintenance and servicing of office equipment like Computers, Photocopiers and Printers | plan | UGX | 12000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
179 | UWSSD | Power extension to water supply systems in selected towns in Umbrellas of Water and Sanitation Authorities | plan | UGX | 600000000 | GOU | ODB | Lumpsum | 2019-09-01 | 2019-09-21 | 2019-10-11 | 2019-10-31 | 2019-11-20
Actual
180 | UWSSD | Supply of Bulk and Micro water meters for Umbrellas of Water and Sanitation Authorities | plan | UGX | 2000000000 | GOU | ODB | Lumpsum | 2019-09-14 | 2019-10-04 | 2019-10-24 | 2019-11-13 | 2019-12-03
Actual
181 | UWSSD | Procurement for Rehabilitation and extensions, of water systems in RGCs and small towns including new water sources, reservoirs, transmission lines and distribution networks | plan | UGX | 800000000 | GOU | ODB | Lumpsum | 2019-09-14 | 2019-10-04 | 2019-10-24 | 2019-11-13 | 2019-12-03
Actual
182 | UWSSD | Purchase of Office ICT equipment | plan | UGX | 50000000 | GOU | ODB | Lumpsum | 2019-09-14 | 2019-10-04 | 2019-10-24 | 2019-11-13 | 2019-12-03
Actual
183 | UWSSD | Procurement for marketing and branding of Umbrellas of Water and Sanitation Authorities to build preference and loyalty and stimulate connectivity to piped water supply lines. | plan | UGX | 400000000 | GOU | ODB | Lumpsum | 2019-09-14 | 2019-10-04 | 2019-10-24 | 2019-11-13 | 2019-12-03
Actual
184 | UWSSD | Purchase of pipes for extensions to be used in small towns and RGC's by the Umbrellas of Water and Sanitation Authorities | plan | UGX | 5000000000 | GOU | ODB | Lumpsum | 2019-09-14 | 2019-09-14 | 2019-10-04 | 2019-10-24 | 2019-11-13
Actual
185 | UWSSD | Supply of a resistivity sounding and imaging system for umbrellas of water and sanitation. | plan | UGX | 350000000 | GOU | ODB | Lumpsum | 2019-10-01 | 2019-10-21 | 2019-11-10 | 2019-11-30 | 2019-12-20
Actual
186 | UWSSD | Procurement of solar energy packages for water supply and sanitation systems in small towns/Rural growth centres in Uganda | plan | UGX | 1000000000 | GOU | ODB | Lumpsum | 2019-10-01 | 2019-10-21 | 2019-11-10 | 2019-11-30 | 2019-12-20
Actual
187 | UWSSD | Supply of 6 No. cesspool emptiers | plan | UGX | 4507400000 | DONOR | OCB | Lumpsum | 2019-10-01 | 2019-10-21 | 2019-11-10 | 2019-11-30 | 2019-12-20
Actual
188 | UWSSD | Supply of 6 no. Vehicles for project implementation and monitoring | Plan | UGX | 1692600000 | DONOR | LCB | Lumpsum | 2019-10-01 | 2019-10-21 | 2019-11-10 | 2019-11-30 | 2019-12-20
Actual
189 | UWSSD | Supply of Office and IT Equipment | Plan | UGX | 606200000 | DONOR | LCB | Lumpsum | 2019-10-01 | 2019-10-21 | 2019-11-10 | 2019-11-30 | 2019-12-20
Actual
190 | UWSSD | Provision of Hotel Services for pre-construction, construction, post construction, training coordination and M&E activities | Plan | UGX | 1000000000 | DONOR | Shopping | Lumpsum | 2019-10-01 | 2019-10-21 | 2019-11-10 | 2019-11-30 | 2019-12-20
Actual
191 | UWSSD | Repair and Maintenance of Vehicles | Plan | UGX | 165000000 | DONOR | Shopping | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
192 | UWSSD | Repair and Maintenance of IT Equipment | Plan | UGX | 82000000 | DONOR | Shopping | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
193 | UWSSD | Supply of stationery and Printing of IEC Materials | Plan | UGX | 20600000 | DONOR | Shopping | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
194 | UWSSD | Supply of tyres | Plan | UGX | 103000000 | DONOR | Shopping | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
195 | UWSSD | Construction of Kyenjojo-Katoke piped water supply systems in Kyenjojo district | Plan | UGX | 27955800000 | DONOR | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
196 | UWSSD | Construction of Bundibugyo piped water supply systems in Bundibugyo district | Plan | UGX | 14427400000 | DONOR | LCB | Admeasurement | 2019-11-28 | 2019-12-28 | 2020-01-27 | 2020-02-26 | 2020-03-27
Actual
197 | UWSSD | Construction of Nakasongola piped water supply systems in Nakasongola District | Plan | UGX | 27056800000 | DONOR | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
198 | UWSSD | Construction of Buikwe Piped water supply systems in Buikwe district | Plan | UGX | 21191600000 | DONOR | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
199 | UWSSD | Construction of Kayunga Busaana piped water supply system Phase II in Kayunga District | plan | UGX | 27056800000 | DONOR | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
200 | UWSSD | Construction of Dokolo Piped water supply system in Dokolo district | Plan | UGX | 14427800000 | DONOR | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
201 | UWSSD | Construction of Kamuli Piped piped water supply systems in Kamuli district | Plan | UGX | 28675000000 | DONOR | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
202 | UWSSD | Construction of Kapchorwa piped water supply system in Kapchorwa district | Plan | UGX | 8115800000 | DONOR | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
203 | UWSSD | Works for Construction of Busia Municipality Water Supply and faecal sludge Sanitation/Facilities System, Source Protection Measures and Sanitation Facilities in Kumi-Nyero-Ngora | Plan | UGX | 38276230232 | World Bank/ GOU | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
204 | UWSSD | Works for Construction of: Lot 1 : Namasale Water Supply and Sanitation System and Sanitation and Koboko Sanitation works Lot 2: Kaliro - Namungalwe Water Supply and Sanitation System Lot 3: Sanitation works for Rukungiri Municipality | Plan | UGX | 27851586966 | World Bank/ GOU | OCB | Admeasurement | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
205 | UWSSD | Supply of 100,000m Pipes and Fittings for Umbrellas of Water and Sanitation under Frame Work Agreement | Plan | UGX | 3692250000 | World Bank/ GOU | OCB | Lumpsum | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
206 | UWSSD | Supply of 25,000 Micro and Bulk Water Meters for Umbrellas of Water and Sanitation under Framework Agreement | Plan | UGX | 2034429750 | World Bank/ GOU | OCB | Lumpsum | 2019-11-12 | 2019-12-12 | 2020-01-11 | 2020-02-10 | 2020-03-11
Actual
207 | UWSSD | Labor requirement for the installation of pipes, fittings and water meters for Umbrella Water & Sanitation Authorities under Framework Agreements in : Lo1: Central, Lot 2: Eastern, Lot 3: South Western, Lot 4: Mid-Western and Lot 5: Northern | Plan | UGX | 3038721750 | World Bank/ GOU | LCB | Lumsum | 2019-12-16 | 2020-01-15 | 2020-02-14 | 2020-03-15 | 2020-04-14
Actual
208 | UWSSD | Supply and Installation of 60 units of Electro-Mechanical equipment for Umbrella Water and Sanitation Authority under Framework Agreement | Plan | UGX | 1831356000 | World Bank/ GOU | LCB | Lumsum | 2019-12-16 | 2020-01-15 | 2020-02-14 | 2020-03-15 | 2020-04-14
Actual
209 | UWSSD/KWSSP | Construction of Morulem Town Piped Water Supply Systems | Plan | UGX | 2200000000 | GOU | ODB | Admeasurement | 2019-12-16 | 2020-01-15 | 2020-02-14 | 2020-03-15 | 2020-04-14
Actual
210 | UWSSD/KWSSP | Construction of Alerek Town Piped Water Supply Systems | Plan | UGX | 1000000000 | GOU | ODB | Admeasurement | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
211 | UWSSD/KWSSP | Expansion of Kacheri Town piped Water Supply Systems | Plan | UGX | 400000000 | GOU | RDB | Admeasurement | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
212 | UWSSD/KWSSP | Construction of Namalu Town Piped Water Supply Systems | Plan | UGX | 800000000 | GOU | ODB | Admeasurement | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
213 | UWSSD/KWSSP | Drilling of 20 Production wells in the townd under Design | Plan | UGX | 700000000 | GOU | ODB | Admeasurement | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
214 | UWSSD/KWSSP | Power Extension to Pump Stations in the Towns of Amudat, Orwamuge and Kacheri | Plan | UGX | 330000000 | GOU | RDB | Admeasurement | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
215 | UWSSD/KWSSP | Construction of Miinistry of Water and Environment Karamoja Regional Office Block Phase One | Plan | UGX | 1500000000 | GOU | ODB | Admeasurement | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
216 | UWSSD | Uniforms, Beddings and Protective Gear | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
217 | UWSSD | ICT Equipment | Plan | UGX | 35000000 | GOU | RFQ | Lumpsum | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
218 | WSDF-N | Framework Contract for Supply Assorted and Printed stationery | Plan | UGX | 226000000 | GoU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
219 | WSDF-N | Purchase of Office and ICT Equipment, including Software | Plan | UGX | 120000000 | GoU | RDB | Lumpsum | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
220 | WSDF-N | Supply and Installation of CC TV Cameras | Plan | UGX | 50000000 | GoU | RFQ | Lumpsum | 2019-11-04 | 2019-11-24 | 2019-12-14 | 2020-01-03 | 2020-01-23
Actual
221 | WSDF-N | Purchase of Office Equipment, Furniture and fittings | Plan | UGX | 60500000 | GoU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
222 | WSDF-N | Supply of kitchen and cleaning materials | Plan | UGX | 96000000 | GoU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
223 | WSDF-N | Tree planting /seedlings and trees for catchment protection | Plan | UGX | 60000000 | GoU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
224 | WSDF-N | Procurement of Fuel Oils and Lubricants | Plan | UGX | 300000000 | GoU | DP | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
225 | WSDF-N | Procurement of Vehicle Tyres | plan | UGX | 50000000 | GoU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
226 | WSDF-N | Supply and installation of visibility materials for completed Towns | Plan | UGX | 150,00,000 | GoU | RDB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
227 | WSDF-N | Procurement of Two Double Cabin Pickup | Plan | UGX | 500000000 | GoU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
228 | WSDF-N | Hotel services for meals and refreshment, workshop Venue, outdoor catering. | Plan | UGX | 180000000 | GoU | RFP | Lumpsum | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09
Actual
229 | WSDF-N | Repair and Maintenance of Motor Vehicles | Plan | UGX | 120000000 | GoU | RFP | Lumpsum | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09
Actual
230 | WSDF-N | Repair and Maintenance of Office Equipment | Plan | UGX | 20000000 | GoU | RFP | Lumpsum | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09
Actual
231 | WSDF-N | Procurement of Advertising Space and Supplements | Plan | UGX | 50000000 | GoU | RFP | Lumpsum | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09
Actual
232 | WSDF-N | Procurement of Security Services | Plan | UGX | 21000000 | GoU | RFP | Lumpsum | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09
Actual
233 | WSDF-N | Procurement of Contractor for the Construction of Moyo Town Council Piped Water Supply System and Sanitation Facilities in Moyo District. | Plan | UGX | 5500000000 | GoU | ODB | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09
Actual
234 | WSDF-N | Procurement of Contractor for the Construction of Bibia/Elegu RGC Piped Water Supply System and Sanitation Facilities in Amuru District. | Plan | UGX | 5000000000 | GoU | ODB | Lumspum | 2019-07-01 | 2019-07-21 | 2019-08-10 | 2019-08-30 | 2019-09-19
Actual
235 | WSDF-N | Procurement of Contractor for the Construction of Padibe RGC Piped Water Supply System and Sanitation Facilities in Lamwo District. | Plan | UGX | 5100000000 | GoU | ODB | Lumspum | 2019-07-01 | 2019-07-21 | 2019-08-10 | 2019-08-30 | 2019-09-19
Actual
236 | WSDF-N | Procurement of Contractor for the Construction of Odramachako RGC Piped Water Supply System and Sanitation Facilities in Arua District | Plan | UGX | 5100000000 | GoU | ODB | Lumspum | 2019-07-01 | 2019-07-21 | 2019-08-10 | 2019-08-30 | 2019-09-19
Actual
237 | WSDF-N | Procurement of Contractor for the Construction of Atiak RGC Piped Water Supply System and Sanitation Facilities in Amuru District. | Plan | UGX | 2500000000 | GoU | ODB | Lumspum | 2019-07-01 | 2019-07-21 | 2019-08-10 | 2019-08-30 | 2019-09-19
Actual
238 | WSDF-N | Procurement of Contractor for the Construction of Barr RGC Piped Water Supply System and Sanitation Facilities in Lira District. | Plan | UGX | 5000000000 | GoU | ODB | Lumspum | 2019-07-01 | 2019-07-21 | 2019-08-10 | 2019-08-30 | 2019-09-19
Actual
239 | WSDF-N | Procurement of contractor to Construct of Yumbe Faecal sludge drying facility | Plan | UGX | 1383249600 | GoU | ODB | Lumspum | 2019-07-01 | 2019-07-21 | 2019-08-10 | 2019-08-30 | 2019-09-19
Actual
240 | WSDF-N | Maintenance of office block | Plan | UGX | 100000000 | GoU | RFQ | Lumspum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
241 | WSDF-N | Procurement of Framework Contract for the Drilling of Production wells in selected RGCs in Northern Uganda | Plan | UGX | 650000000 | GoU | ODB | Admeasuremet | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
242 | WSDF-N | Procurement of Contractor for the Extension of 3 Phase Grid Power to Ministry of Water and Environment Offices in Lira District. | Plan | UGX | 50000000 | GoU | RFQ | Admeasuremet | 2019-07-31 | 2019-08-10 | 2019-08-20 | 2019-08-30 | 2019-09-09
Actual
243 | WSDF-N | Construction of Olujobo Refugee Settlement Camp Piped WSSS in Arua District | Plan | UGX | 1595297461 | GoU | ODB | Admeasuremet | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
244 | WSDF-N | Rehabilitation and Extension of Ayilo II Refugee Settlement Camp Piped WSSS Adjumani District | Plan | UGX | 1652000000 | GoU | ODB | Admeasuremet | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
245 | WSDF-N | Construction of Ofua III and Omugo VI Refugee Settlement Camp Piped WSSS in Arua District | Plan | UGX | 2386690455 | GoU | ODB | Admeasuremet | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
246 | WSDF-N | Construction of Bidibidi Zone V Refugee Settlement Camp Piped WSS in Yumbe District | Plan | UGX | 2200000000 | GoU | ODB | Admeasuremet | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
247 | WSDF-N | Extension of Ranch I WSSS to Panyadoli Village | Plan | UGX | 500000000 | GoU | RDB | Admeasuremet | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
248 | WFPRC-N | Works for weed control at Leye dam in Kole District. | Plan | UGX | 760000000 | GoU | ODB | Admeasuremet | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
249 | WFPRC-N | Supply of Construction Materials for Construction of Valley Tanks and Small Scale Irrigation Schemes in Upper central, Northern and West Nile Regions | Plan | UGX | 2200000000 | GOU | ODB | Admeasuremet | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
250 | WFPRC-N | Supply of food ratios for construction WfP Facilities | Plan | UGX | 300000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
251 | WFPRC-N | Supply and Installation of solar equipment, water pumps and generators for construction of Water for Production facilities in Upper central, Northern and West Nile Regions | Plan | UGX | 2200000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
252 | WFPRC-N | Supply of Fuel, Oils and Lubricants for Construction of Valley Tanks and Small Scale Irrigation Schemes in Upper central, Northern and West Nile Regions | Plan | UGX | 1000000 | GOU | DP | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
253 | WFPRC-N | Supply of inputs (Pipes, fittings, fixtures, valves, drip lines and sprinklers) for construction of micro-irrigation systems | Plan | UGX | 2200000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
254 | WFPRC-N | Supply of agronomy inputs for small scale irrigation systems in Upper central, Northern and West Nile Regions | Plan | UGX | 1200000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
255 | WFPRC-N | Supply of protective gears | Plan | UGX | 350000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
256 | WFPRC-N | procurement of IT equipment and servicing including 01 printer, 3 laptops, 2 GPSs and 01 Camera | Plan | UGX | 35000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
257 | WFPRC-N | Visibility materials (t-shirts, banners, posters, caps, diareis, umbrellas, calendars, | Plan | UGX | 110000000 | GOU | RDB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
258 | WFPRC-N | Office furniture and fittings | Plan | UGX | 50000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
259 | WFPRC-N | Vehicle maintenance and Repair, Supply of Tyres and tubes | Plan | UGX | 200000000 | GOU | RDB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
260 | WFPRC-N | Office stationery including (Cartridges, Toner), Printing and Photocopying Services | Plan | UGX | 33000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
261 | WFPRC-N | Supply of Office Consumables (refer to the attached list) | Plan | UGX | 30000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
262 | WFPRC-N | Procurement of 2No. 20 feet Containers | Plan | UGX | 30000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
263 | WFPRC-N | Supply and Installation of Bulk Water Meters for Olweny Irrigation Scheme | plan | UGX | 100000000 | GOU | RDB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
264 | WFPRC-N | Supply of Equipment parts, Lubricants and servicing of Earth Moving Equipment | Plan | UGX | 580000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
265 | WFPRC-N | Purchase of Digital Level for construction of WfP Facilities | Plan | UGX | 50000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
266 | WFPRC-N | Hotel hire (Conference hall, accommodation, Meals and Drinks) and Catering services | Plan | UGX | 100000000 | GOU | RFP | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
267 | WFPRC-N | Telecommunications services including internet and office connectivity | Plan | UGX | 24000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
268 | WFPRC-N | Advertising & PR, Media, Radio Talk Shows, | Plan | UGX | 65000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
269 | WFPRC-N | Hire of specialised construction equipment for Construction of Water for Production Facilities | Plan | UGX | 300000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
270 | UNWMZ | Procurement of lab equipment, testing kits, consumables and reagents | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
271 | UNWMZ | Printing, Stationery, Binding | Plan | UGX | 10000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
272 | UNWMZ | Procurement of vehicle Tyres | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
273 | UNWMZ | Computers and Accessories | Plan | UGX | 10000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
274 | UNWMZ | Internet Services | Plan | UGX | 5000000 | GOU | MICRO | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
275 | UNWMZ | M/V repairs, service, oils and lubricants | Plan | UGX | 100000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
276 | UNWMZ | IEC and awareness raising materials (T-Shirts and caps, Corporate shirts, banners, tier drops, year calendars, printing of brochures) | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
278 | UNWMZ | Restoration and rehabilitation of degraded micro catchments | Plan | UGX | 350000000 | GOU | RDB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
279 | WSDF-E | Construction of Acowa Town Water Supply System. | plan | UGX | 2400000000 | GOU | ODB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
280 | WSDF-E | Construction of Idudi Town Water Supply System | plan | UGX | 6500000000 | GOU | ODB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
281 | WSDF-E | Construction of Bulangira Town Water Supply Systems | Plan | UGX | 2470000000 | GOU | ODB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
282 | WSDF-E | Construction of Nasutani GFS | Plan | UGX | 500000000 | GOU | RDB | Admeasurement | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
283 | WSDF-E | Construction of Manafwa Town Council Water Supply Systems | Plan | UGX | 4500000000 | GOU | OBD | Admeasurement | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01 | 2020-03-21
Actual
284 | WSDF-E | Construction of Tubur Water Supply Systems | Plan | UGX | 3700000000 | GOU | OBD | Admeasurement | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01 | 2020-03-21
Actual
285 | WSDF-E | Construction of Ngenge Water Supply Systems | plan | UGX | 7900000000 | GOU | OBD | Admeasurement | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01 | 2020-03-21
Actual
286 | WSDF-E | Extension of Buyende TWSS | plan | UGX | 500000000 | GOU | RDB | Admeasurement | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01 | 2020-03-21
Actual
287 | WSDF-E | Construction of Kanapa WSS | plan | UGX | 1100000000 | GOU | RDB | Admeasurement | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01 | 2020-03-21
Actual
288 | WSDF-E | Construction of Bubwaya TWSS | plan | UGX | 400000000 | GoU | RDB | Admeasurement | 2020-01-01 | 2020-01-21 | 2020-02-10 | 2020-03-01 | 2020-03-21
Actual
289 | WSDF-E | Procurement of office ICT equipment | plan | UGX | 100000000 | GoU | RFQ | Lumpsum | 2020-03-01 | 2020-03-11 | 2020-03-21 | 2020-03-31 | 2020-04-10
Actual
290 | WSDF-E | Construction of Regional Faecal Sludge Treatment Facility. | plan | UGX | 2000000000 | GoU | ODB | Admeasurement | 2020-03-01 | 2020-03-21 | 2020-04-10 | 2020-04-30 | 2020-05-20
Actual
291 | WSDF-E | Supply of Furniture and fittings | plan | UGX | 100000000 | GoU | RFQ | Lumpsum | 2020-03-01 | 2020-03-11 | 2020-03-21 | 2020-03-31 | 2020-04-10
Actual
292 | WSDF-E | Maintenance-Vehicles | plan | UGX | 60000000 | GoU | RFQ | Lumpsum | 2020-03-01 | 2020-03-11 | 2020-03-21 | 2020-03-31 | 2020-04-10
Actual
293 | WSDF-E | Maintenance-Machines & Equipment | plan | UGX | 4000000 | GoU | MICRO | Lumpsum | 2020-03-01 | 2020-03-11 | 2020-03-21 | 2020-03-31 | 2020-04-10
Actual
294 | WSDF-E | Hire of venue | plan | UGX | 40000000 | GoU | RFQ | Lumpsum | 2020-03-01 | 2020-03-11 | 2020-03-21 | 2020-03-31 | 2020-04-10
Actual
295 | WSDF-E | Advertising Public Relations | plan | UGX | 40000000 | GoU | RFQ | Lumpsum | 2020-03-01 | 2020-03-11 | 2020-03-21 | 2020-03-31 | 2020-04-10
Actual
296 | WSDF-E | Staff welfare & Entertainment | plan | UGX | 8000000 | GoU | RFQ | Lumpsum | 2020-03-01 | 2020-03-11 | 2020-03-21 | 2020-03-31 | 2020-04-10
Actual
297 | WSDF-E | Printing, Stationery & Binding | plan | UGX | 113000000 | GoU | RDB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
298 | WSDF-E | Fuel, Lubricants & Oils | Plan | UGX | 207000000 | GoU | RDB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
299 | WSDF-E | Small Office Equipment | Plan | UGX | 8000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
300 | WSDF-E | Uniforms and Protective Gear | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
301 | WSDF-E | Supply of Tyres | Plan | UGX | 20000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
302 | WSDF-E | Survey equipment | plan | UGX | 100000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
303 | WESLD | Stationery | plan | UGX | 48000000 | Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
304 | WESLD | Service and repair of motor vehicles | plan | UGX | 72000000 | Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
305 | WESLD | Newspaper supplements | Plan | UGX | 90000000 | Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
306 | WESLD | Procurement of hotel services for JSR 2019 | Plan | UGX | 250000000 | Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
307 | WESLD | Printing of SPR 2019 | Plan | UGX | 100000000 | Donor | RFQ | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20
Actual
308 | WESLD | Printing of SPR 2019 popular version | Plan | UGX | 60000000 | Donor | RFQ | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20
Actual
309 | WESLD | Distribution fo the popular version in News papers | Plan | UGX | 40000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
310 | WESLD | Designing and printing of MWE Calendars 2020 | plan | UGX | 50000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
311 | WESLD | Printing of the Economic Study | plan | UGX | 170000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
312 | WESLD | Procurement of hotel services for JTR 2020 | Plan | UGX | 60000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
313 | WESLD | Procurement of stationery for JTR 2020 | plan | UGX | 65000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
314 | WESLD | Procurement of hotel services for the SPR retreat | Plan | UGX | 20000000 | Donor | RFQ | Lumpsum | 2019-08-01 | 2019-08-21 | 2019-09-10 | 2019-09-30 | 2019-10-20
Actual
315 | WESLD | Procurement of stationery for JSR 2019 | plan | UGX | 60000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
316 | WESLD | Software (ArcGIS, AutoCAD, Kaspersky, Microsoft) | Plan | UGX | 100000000 | GOU | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
317 | WESLD | Printers, UPS' and Projectors | Plan | UGX | 60000000 | GOU | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
318 | WESLD | Procurement of Computers and Accessories | Plan | UGX | 60000000 | GOU | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
319 | WESLD | Printing of the Training Plan for the staff of the MWE | Plan | UGX | 45000000 | GOU | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
320 | WESLD | Printing of the Guidelines for Borehole Siting,Drilling Supervision, and Pump Testining | Plan | UGX | 120000000 | GOU | RDB | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
321 | WESLD | Printing of CD plans | Plan | UGX | 45000000 | GOU | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
322 | WESLD | Printing of the Harmonised CD plans | Plan | UGX | 45000000 | GOU | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
323 | WESLD | Procurement of hotel services for gender capacity building trainings | Plan | UGX | 50000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
324 | WESLD | Procurement of printing services of the community resource book | Plan | UGX | 190000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
325 | WESLD | Procurement of Hotel Serices for HIV/AIDS workshops | Plan | UGX | 56000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
326 | WESLD | Printing of HIV/ AIDS mainstreaming Guidelines for WATSAN | Plan | UGX | 50000000 | Donor | RFQ | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
327 | WESLD | Construction of institutional sanitation facilities | Plan | UGX | 500000000 | Donor | RDB | Lumpsum | 2019-10-31 | 2019-11-10 | 2019-11-20 | 2019-11-30 | 2019-12-10
Actual
328 | IA | Computer supplies | Plan | UGX | 50000000 | GOU | RFQ | Lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31 | 2020-02-10
Actual
329 | IA | Assorted office stationery | Plan | UGX | 10000000 | GOU | RFQ | Lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31 | 2020-02-10
Actual
330 | IA | Small office equipment | Plan | UGX | 45000000 | GOU | RFQ | Lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31 | 2020-02-10
Actual
331 | D/DEA | Computer supplies and information Technology, servicing of Computers and photocopiers | Plan | UGX | 11250000 | GOU |  | Lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31 | 2020-02-10
Actual
332 | D/DEA | small Office equipment | Plan | UGX | 6000000 | GOU |  | Lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31 | 2020-02-10
Actual
334 | D/DEA | Books, Periodical and newspapers | Plan | UGX | 1350000 | GOU |  | Lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31 | 2020-02-10
Actual
335 | D/DEA | Stationery, Photocopying and Bindding | Plan | UGX | 2250000 | GOU |  | Lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31 | 2020-02-10
Actual
336 | D/DEA | Fuel, Lubricants and Oil. | Plan | UGX | 14426750 | GOU |  | Lumpsum | 2020-01-01 | 2020-01-11 | 2020-01-21 | 2020-01-31 | 2020-02-10
Actual
337 | UWSSD | Procurement of Services for Motor Vehichle Maintenance and Repairs | Plan | UGX | 75000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Acatual
338 | UWSSD | Procurement of Security services | Plan | UGX | 24000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
339 | UWSSD | Hotel Services, Workshops and Seminars | Plan | UGX | 80000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
340 | UWSSD | Procurement of Stationery and printing of IEC materials | Plan | UGX | 200000000 | GOU | RDB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
341 | UWSSD | Purchase of Office and ICT Equipments including Software | Plan | UGX | 50000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
342 | UWSSD | Supply and Installation of pumps and Solar Packages in 3 towns Under KUWS (Lorengedwat, Lokitelaebu and Orwamuge | Plan | UGX | 401000000 | GOU | ODB | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28
Actual
343 | UWSSD | Procurement of a Contractor for Construction of China-Uganda Liaoshen Industrial Park in Kapeeka town Council | Plan | UGX | 55000000000 | GOU | ODB | Admeasurement | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28
Actual
344 | UWSSD | Advertising and Public Relations | Plan | UGX | 40000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
345 | UWSSD | Printing, Stationery, Photocopying and Binding | plan | UGX | 110000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
346 | UWSSD | Computer Supplies & IT Services | Plan | UGX | 60000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
347 | UWSSD | Staff Training | Plan | UGX | 7000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
348 | UWSSD | Hire of Venue (chairs, projector, etc) | Plan | UGX | 16000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
349 | REDD+ | worshops and seminars | Plan | UGX | 71000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
350 | REDD+ | Printing and Stationery | Plan | UGX | 30900000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
351 | REDD+ | Fuel lubricants and oil | Plan | UGX | 28000000 | GOU/Donor | DP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actaual
352 | REDD+ | Vehicle mantainence | Plan | UGX | 30000000 | GOU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
353 | FSSD | Fuel | plan | UGX | 54000000 | GOU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
354 | REDD+ | Purchase of computer accessories and software | Plan | UGX | 30000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actaul
355 | REDD+ | Office Cleaning materials | plan | UGX | 5000000 | GoU/Donor | MICRO | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
actual
356 | REDD+ | Renovation of office building | Plan | UGX | 30000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
357 | REDD+ | Purchase of Office consumables, Toner | Plan | UGX | 15000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
358 | REDD+ | Small Office Equipment | Plan | UGX | 5000000 | GoU/Donor | MICRO | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
359 | REDD+ | Purchase of Furniture & Fittings, and Curtains | Plan | UGX | 30000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
360 | REDD+ | Media/Publicity, Website upgrades | plan | UGX | 30000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
361 | REDD+ | Magazines. Periodicals & Newspapers | Plan | UGX | 15000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
362 | REDD+ | Welfare and Entertainment | Plan | UGX | 20000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
363 | REDD+ | Staff training | Plan | UGX | 20000000 | GoU/Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
364 | REDD+ | Electricity | Plan | UGX | 4000000 | GOU | DP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
365 | REDD+ | Water | Plan | UGX | 4000000 | GOU | DP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
366 | REDD+ | Telecommunications | Plan | UGX | 4000000 | GOU | DP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
367 | REDD+ | Travel Abroad | Plan | UGX | 50000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
368 | ITWAD | Procure printing services for Transboundary WR reports, Technical Documentation | Plan | UGX | 160000000 | GOU | RDB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
369 | ITWAD | Procure services for intersectoral coordination meetings | Plan | UGX | 80000000 | GOU | RFP | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
370 | ITWAD | Procure services for NBI, LVBC, IGAD, AMCOW governance meetings | plan | UGX | 200000000 | GOU | RFP | Lumpsum | 2019-07-31 | 2019-08-20 | 43717 | 2019-09-29 | 2019-10-19
Actual
371 | ITWAD | Procurement of Air tickets for regional and international foras (NBI, LVBC, AMCOW, IGAD, Bilateral engagements with South Sudan, D.R. Congo, Tanzania, Sudan, Rwanda, Egypt, Ethiopia etc.) | plan | UGX | 150000000 | GOU | RDB | Lumpsum | 2019-07-31 | 2019-08-20 | 43717 | 2019-09-29 | 2019-10-19
Actual
372 | ITWAD | Procurement of 1 vehicle for the department | plan | UGX | 240000000 | GOU | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 43717 | 2019-09-29 | 2019-10-19
Actual
373 | ITWAD | Procurement of Office Stationery, Sundries, office equipment | plan | UGX | 80000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
374 | ITWAD | Procurement of vehicle tyres and spares, O&M of vehicles, Oils and lubricants | plan | UGX | 100000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
375 | CCD | Purchase of Air tickets | Plan | UGX | 600000000 | GoU - Donor | ODB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
376 | CCD | Purchase of Tyres | plan | UGX | 40000000 | GoU - Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
377 | CCD | Vehicle Repairs and maintenance | plan | UGX | 50000000 | GoU - Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
378 | CCD | Purchase of Vehicles for the Department | plan | UGX | 720000000 | GoU - Donor | ODB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
379 | CCD | Hotel facilities for workshops | plan | UGX | 355000000 | GoU - Donor | ODB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
380 | CCD | Printing Calendars, Diaries Policy briefs, brochures, posters for climate change awareness, Tshirts, Pull ups , umbrellas and Banners | plan | UGX | 225000000 | GoU - Donor | ODB | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
381 | CCD | Printing of the National Climate Change Policy , The climate Change Bill , popular version and the Paris Agreements | Plan | UGX | 150000000 | GoU - Donor | RDB | LUMPSUM | 2019-07-31 | 2019-08-30 | 43737 | 43767 | 2019-11-28
Actual
382 | CCD | Generator/Solar sytem | plan | UGX | 60000000 | GoU - Donor | RFQ | Lumpsum | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
383 | CCD | Office Refurbishment and burglar proofing | plan | UGX | 200000000 | GoU - Donor | RDB | Lumpsum | 2019-07-31 | 2019-08-30 | 43737 | 2019-10-29 | 2019-11-28
Actual
384 | CCD | Purchase of Stationery | plan | UGX | 70000000 | GoU - Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
385 | CCD | Office Cleaning Services | plan | UGX | 66000000 | GoU - Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
386 | CCD | Purchase of cleaning materials | plan | UGX | 20000000 | GoU - Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
| CCD | Furniture and fittings | plan | UGX | 50000000 | GoU - Donor | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
387 |  |  | Actual
388 | CCD | Purchase of IT Equipment and accessories (Desktops, printers, Laptops, iPads and others) | plan | UGX | 250000000 | GoU - Donor | ODB | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
389 | CCD | Purchase, installation and servicing of Air Conditioners | plan | UGX | 50000000 | GoU - Donor | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
390 | CCD | purchase of Soft ware , internet services and renewal of licences | plan | UGX | 120000000 | GoU - Donor | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
391 | CCD | Annual Subscriptions: UNFCCC, Magazines and others | plan | UGX | 40000000 | GoU - Donor | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
392 | CCD | Procurement of side room for the UNFCC -COP25 | plan | UGX | 200000000 | GoU - Donor | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
393 | CCD | Purchase of carpets for the Board rooms and offices | plan | UGX | 70000000 | GoU - Donor | RFQ | Lumpsum | 2019-07-31 | 2019-08-20 | 2019-09-09 | 2019-09-29 | 2019-10-19
Actual
394 | CCD | Machinery and equipment | plan | UGX | 300000000 | GoU - Donor | RFQ | Lumpsum | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29
Actual
395 | CCD | Production of Film documentary | plan | UGX | 100000000 | GoU - Donor | RFQ | Lumpsum | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29
Actual
396 | CCD | Servicing of IT Equipment and fire extinguishers | plan | UGX | 25000000 | GoU - Donor | RFQ | Lumpsum | 2019-08-31 | 2019-09-30 | 2019-10-30 | 2019-11-29 | 2019-12-29
Actual
397 | LEAF II | Construction of a Surveillance Station and Research Station in Hoima District | plan | UGX | 1528400000 | Donor/GoU | ODB | Admeasurement | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19
Actual
398 | LEAF II | Civil works for fill and completion of parking space at Rwenshama Landing Site | plan | UGX | 450000000 | GOU | ODB | Admeasurement | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19
Actual
399 | LEAF II | Installation/demonstration of 03 cages | plan | UGX | 111300000 | Donor/GoU | ODB | Admeasurement | 2019-08-31 | 2019-09-20 | 2019-10-10 | 2019-10-30 | 2019-11-19
Actual
400 | LEAF II | Minor renovataion of DFR Offices in Entebbe | plan | UGX | 50000000 | GOU | RFQ | Admeasurement | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03
Actual
401 | LEAF II | Starter kit for livelihood activities | plan | UGX | 261600000 | Donor | Shopping | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03
Actual
402 | LEAF II | 1 Research Vessel | plan | UGX | 2976000000 | Donor | ODB | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03
Actual
403 | LEAF II | 1 Project vehicles | plan | UGX | 150000000 | Donor | Shopping | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03
Actual
404 | LEAF II | Office IT equipment (laptops, printers, software and IT accessories) | plan | UGX | 27900000 | Donor | Shopping | Lumpsum | 2019-07-15 | 2019-08-04 | 2019-08-24 | 2019-09-13 | 2019-10-03
Actual
405 | LEAF II | Small Office Equipment | plan | UGX | 18600000 | Donor | Shopping | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
406 | LEAF II | Supply of stationery, printing and binding materials and services inclusive of toners for printers and photocopiers | plan | UGX | 22320000 | Donor | Shopping | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
407 | LEAF II | servicing and maintenance of office equipment such as photocopiers, printers, computers, vehicles, specialized equipment, air conditioners, etc. | plan | UGX | 202380000 | Donor | Shopping | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
408 | LEAF II | Office cleaning materials | plan | UGX | 4390000 | Donor | Shopping | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
409 | LEAF II | Supply of air tickets | plan | UGX | 45000000 | Donor | RFQ | Framework | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
410 | LEAF II | Security Services | plan | UGX | 5680000 | Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
411 | LEAF II | Supply of Hotel Services | Plan | UGX | 37200000 | Donor | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
412 | LEAF II | Provision of Communication Services | plan | UGX | 6510000 | Donor/GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
413 | AWMZ | Awareness Raising Material | plan | UGX | 10000000 | Donor/GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
414 | AWMZ | Construction of Soil & Water Conservation Structures | Plan | UGX | 400000000 | Donor/GoU | ODB | Admeasurement | 2019-07-31 | 2019-08-30 | 2019-09-29 | 2019-10-29 | 2019-11-28
Actual
415 | AWMZ | Supply of Stationery | Plan | UGX | 20000000 | Donor/GoU | ODB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
416 | AWMZ | Supply of Office Cleaning Materials and Consumables | plan | UGX | 21000000 | Donor/GoU | ODB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
417 | AWMZ | Supply of Furniture | plan | UGX | 20000000 | Donor/GoU | ODB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
418 | AWMZ | Supply of Tyres | Plan | UGX | 18000000 | Donor/GoU | ODB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
419 | AWMZ | Supply of 2 No. Computers and Accessories | Plan | UGX | 15000000 | Donor/GoU | ODB | Lumsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
420 | AWMZ | Supply of Laboratory Consumables | Plan | UGX | 1400000000 | Donor/GoU | ODB | Lumsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
421 | AWMZ | supply of Laboratory Equipment | Plan | UGX | 1500000000 | Donor/GoU | ODB | Lumsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
422 | WfP | Construction completion of Rwengaaju Model Village Irrigation Scheme in Kabarole District | Plan | UGX | 27301186392 | GOU | ODB | Admeasurement | 2019-07-21 | 2019-08-10 | 2019-08-30 | 2019-09-19 | 2019-10-09
Actual
423 | WfP | Construction of Ojama earth dam and multipurpose water systems and facilities in Serere District | Plan | UGX | 7500000000 | GOU | ODB | Admeasurement | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28
Actual
424 | WfP | Construction of Kawumu Irrigation Scheme in Luwero District | Plan | UGX | 2500000000 | GOU | ODB | Admeasurement | 2019-07-21 | 2019-08-20 | 2019-09-19 | 2019-10-19 | 2019-11-18
Actual
425 | WfP | Procurement of services for major repair of Earth Moving equipment | Plan | UGX | 150000000 | GOU |  | Lumpsum | 2019-07-21 | 2019-08-20 | 2019-09-19 | 2019-10-19 | 2019-11-18
Actual
426 | WfP | Procurement of 5No. Earth moving equipment units (each compromising Excavator, Bull Dozer, Tipper Truck and Water Bowser) | Plan | UGX | 6000000000 | GOU | ODB | Lumpsum | 2019-07-21 | 2019-08-20 | 2019-09-19 | 2019-10-19 | 2019-11-18
Actual
427 | WfP | Procurement of Design, supply, and installation of 8No. Hydraulic ram pump systems on selected wfp facilities Unit | Plan | UGX | 350000000 | GOU | ODB | Lumpsum | 2019-07-21 | 2019-08-20 | 2019-09-19 | 2019-10-19 | 2019-11-18
Actual
428 | WfP | Procurement of Stationery Items, Cartridges and Tonners | Plan | UGX | 50000000 | GOU | RFQ | Lumpsum | 2019-07-21 | 2019-08-20 | 2019-09-19 | 2019-10-19 | 2019-11-18
Actual
429 | WfP | Procurement of ICT Equipment (Desktops, Laptops, Printers, UPS, Photocopiers and Scanners) for Water for Production Department | Plan | UGX | 100000000 | GOU | ODB | Lumpsum | 2019-07-21 | 2019-08-20 | 2019-09-19 | 2019-10-19 | 2019-11-18
Actual
430 | HRM | Printing of the client's charter booklets | Plan | UGX | 48905100 | GOU | RFP | Lumpsum | 2019-07-21 | 2019-08-20 | 2019-09-19 | 2019-10-19 | 2019-11-18
Actual
431 | WSDF-SW-EURECCA | Procure IT services and computers accessories | Plan | UGX | 10000000 | Donor/GoU | RFP | Lumpsum | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019 | 26th-Oct-2019
Actual
Plan
432 | WSDF-SW-EURECCA | Supply of Stationery | Plan | UGX | 8000000 | Donor/GoU | RFP | Lumpsum | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019 | 26th-Oct-2019
Actual
433 | WSDF-SW-EURECCA | Supply of Office Consumables | Plan | UGX | 5000000 | Donor/GoU | Micro | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
434 | WSDF-SW-EURECCA | Procure venue, hotel and catering services for workshops, meetings and seminars | Plan | UGX | 216000000 | Donor/GoU | ODB | Lumpsum | 2019-08-21 | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019
Actual
435 | WSDF-SW-EURECCA | Vehicle tyres, repair services and spares | Plan | UGX | 17000000 | Donor/GoU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
436 | WSDF-SW-EURECCA | Supply of Assorted Tree seedlings (150,000 No) | Plan | UGX | 330000000 | Donor/GoU | ODB | Lumpsum | 2019-08-21 | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019
Actual
437 | WSDF-SW-EURECCA | Supply and production of cook stoves | Plan | UGX | 33000000 | Donor/GoU | RFQ | Lumpsum | 2019-08-21 | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019
Actual
438 | WSDF-SW-EURECCA | Supply of Inputs for demarcation and restoration of 4No. wetland systems | Plan | UGX | 378000000 | Donor/GoU | ODB | Lumpsum | 2019-08-21 | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019
Actual
439 | WSDF-SW-EURECCA | Supply of Inputs for demarcation and restoration of 4No. River banks sections | Plan | UGX | 240000000 | Donor/GoU | ODB | Admeasurement | 2019-08-21 | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019
Actual
440 | WSDF-SW-EURECCA | Inputs for construction of water harvesting and biophysical structures | Plan | UGX | 310000000 | Donor/GoU | ODB | Admeasurement | 2019-08-21 | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019
Actual
441 | WSDF-SW-EURECCA | setting up of demonstration plots | Plan | UGX | 400000000 | Donor/GoU | ODB | Admeasurement | 43698 | 23rd-Aug-19 | 30th-Aug-2019 | 27th-Sept-2019 | 27th-Sept-2019
Actual
442 | VWMZ | Restoration and rehabilitation of degraded micro catchments | Plan | UGX | 500000000 | GOU | RDB | Admeasurement | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
443 | VWMZ | Rehabilitation of office buildings and other non residential infrastructure | Plan | UGX | 120000000 | GOU | RDB | Admeasurement | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
444 | VWMZ | procurement of IT services and computers accessories, staionery and other office accessories | Plan | UGX | 25000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
|  | procurement of IT services and computers accessories, staionery and other office accessories | Actual
445 | VWMZ | Procure venue, hotel and catering services for workshops, meetings and seminars | Plan | UGX | 65000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
446 | VWMZ | Procure vehicle, tyres, repair services and spares | Plan | UGX | 44000000 | GOU | ODB | Framework | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
447 | VWMZ | Procure necessary water quality field equipment and consumables | Plan | UGX | 30000000 | GOU | ODB/Framework | Lumpsum/ Framework | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
448 | VWMZ | Procure awareness and visibility materials | Plan | UGX | 250000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
449 | WSDF-SW | Construction of Solar Mini Water Supply Systems in Nyakatonzi and Bigando RGCs in Kasese District | Plan | UGX | 1500000000 | GOU | ODB | Admeasurement | 08th-Jan-2020 | 26th-Jun-19 | 04th-July-2019 | 01st-Aug-2019 | 01st-Aug-2019
Actual
450 | WSDF-SW | Connstruction of Igorora TC Water Supply and Sanitation System in Ibanda District | Plan | UGX | 1900000000 | GOU | ODB | Admeasurement | 08th-Jan-2020 | 04th-Oct-19 | 10th-Oct-2019 | 07th-Nov-2019 | 07th-Nov-2019
Actual
451 | WSDF-SW | Connstruction of Karago II Town Water Supply and Sanitation System in Kabarole District | Plan | UGX | 2000000000 | GOU | ODB | Admeasurement | 08th-Jan-2020 | 10th-Jan-2020 | 15th-Jan-2020 | 13th-Feb-2020 | 13th-Feb-2020
Actual
452 | WSDF-SW | Construction of Rushango TC Water Supply and Sanitation System | Plan | UGX | 7500000000 | GOU | ODB | Admeasurement | 08th-Jan-2020 | 10th-Jan-2020 | 15th-Jan-2020 | 13th-Feb-2020 | 13th-Feb-2020
Actual
453 | WSDF-SW | Construction of Bethelehem Town Council Water Supply System | Plan | UGX | 8200000000 | GOU | ODB | Admeasurement | 08th-Jan-2020 | 10th-Jan-2020 | 15th-Jan-2020 | 13th-Feb-2020 | 13th-Feb-2020
Actual
454 | WSDF-SW | Construction of an Office Building for the Ministry of Water & Environment-South West Regional Offices in Mbarara | Plan | UGX | 300000000 | GOU | RDB | Admeasurement | 08th-Jan-2020 | 10th-Jan-2020 | 15th-Jan-2020 | 13th-Feb-2020 | 13th-Feb-2020
Actual
455 | WSDF-SW | Construction of Kibugu Town Water Supply System | Plan | UGX | 3593000000 | GOU | ODB | Admeasurement | 08th-Jan-2020 | 10th-Jan-2020 | 15th-Jan-2020 | 13th-Feb-2020 | 13th-Feb-2020
Actual
456 | WSDF-SW | Procurement for drilling of production wells (24 No.) | Plan | UGX | 1568000000 | GOU | ODB | Admeasurement | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
457 | WSDF-SW | Office Maintanance-Civil and Electrical | Plan | UGX | 400000000 | GOU | RDB | Admeasurement | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
458 | WSDF-SW | Supply of Assorted Stationery/Printed stationery | Plan | UGX | 140000000 | GOU | RDB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
459 | WSDF-SW | Advertising & Public relations | Plan | UGX | 100000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
460 | WSDF-SW | Security Services | Plan | UGX | 16000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
461 | WSDF-SW | Supply of Consumables/General goods | Plan | UGX | 36000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
462 | WSDF-SW | Provision of Hotel Services | Plan | UGX | 100000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
463 | WSDF-SW | Welfare and Entertainment | Plan | UGX | 48000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
464 | WSDF-SW | Supply of Office Furniture | Plan | UGX | 200000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
465 | WSDF-SW | Supply of Fuel, Lubricants and Oils | Plan | UGX | 243000000 | GOU | ODB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
466 | WSDF-SW | Motor Vehicle maintenance and Supply of Motor vehicle tyres | Plan | UGX | 200000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
467 | WSDF-SW | Computer Supplies and Information Technology | Plan | UGX | 71000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
468 | WSDF-SW | Telecommunication | Plan | UGX | 10000000 | GOU | RFP | Lumpsum | 6th-Sept-19 | 6th-Sept-19 | 9th-Sept-19 | 16th-Sept-19 | 16th-Sept-19
Actual
469 | WSDF-SW | Cleaning Services | Plan | UGX | 32000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
470 | WSDF-SW | Garbage Collection & Disposal | Plan | UGX | 7000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
471 | WSDF-SW | Maintanance-Machinery, Equipment & Furniture | Plan | UGX | 12000000 | GOU | RFP | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
472 | WSDF-SW | Supply of a Generator | Plan | UGX | 100000000 | GOU | RFQ | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
473 | WFPRC-SW | Construction of 6No WfP facilities under in Isingiro, Kyotera Rakai, Gomba and Lwengo districts using Equipment through force account mechanism including abstraction | Plan | UGX | 2280000000 | GOU | ODB | Ademeasurement | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
474 | WFPRC-SW | Construction of 10 No solar pumped small scale irrigation schemes in selected Districts | Plan | UGX | 3121000000 | GOU | ODB | Ademeasurement | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
475 | WFPRC-SW | Construction of solar pumped small scale irrigation schemes in selected Districts | Plan | UGX | 4058000000 | GOU | ODB | Ademeasurement | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
476 | WFPRC-SW | Construction of Kyahi and Kyenshama Dams in Gomba and Mbarara Districts for multipurpose uses | Plan | UGX | 4050000000 | GOU | ODB | Lumpsum | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4 | Q1-Q4
Actual
477 | WFPRC-SW | Construction of small scale irrigation schemes in Ntovu in Rakai District and Mbulamu in Mpigi District | Plan | UGX | 1,800,000,000 | GOU | ODB | Ademeasurement | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
|  |  | Actual |  | 1,686,442,076
478 | WFPRC-SW | Construction of small scale irrigation schemes in Nyarulambi in Kanungu District and Garuka in Rukungiri District | Plan | UGX | 2,000,000,000 | GOU | ODB | Ademeasurement | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
|  |  | Actual |  | 1,975,957,688
479 | WFPRC-SW | Construction of small scale irrigation schemes in Kyamugenzi in Hoima District and Isunga in Kibaale District | Plan | UGX | 1,700,000,000 | GOU | ODB | Ademeasurement | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
|  |  | Actual |  | 1,509,133,628
480 | WFPRC-SW | Construction of small scale irrigation schemes in kagulube in Kalangala District and Bukwaya in Buvuma District | Plan | UGX | 2000000000 | GOU | ODB | Ademeasurement | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
|  |  | Actual |  | 1777457151
481 | WFPRC-SW | Construction of small scale irrigation schemes in Buyojwa in Isingiro District and Mabanda in Buhweju District | Plan | UGX | 1600000000 | GOU | ODB | Ademeasurement | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
|  |  | Actual |  | 1411215662
482 | WFPRC-SW | Office Furniture and office fittings, Office Equipment, stationary and Maintenance of office and ICT equipment. | Plan | UGX | 40000000 | GOU | RFQ | Lumpsum/Framework | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
483 | WFPRC-SW | Training and Capacity building staff and district staff | Plan | UGX | 92,000,000 | GOU | Lump sum | Lumpsum/ Time based | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
484 | WFPRC-SW | Purchase of spare parts for Earth Moving machines | Plan | UGX | 200,000,000 | GOU | RDB | Lumpsum | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
485 | WFPRC-SW | Vehicle tyres, Repair and Mantainence | Plan | UGX | 55,000,000 | GOU | ODB | Lumpsum/ Framework | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
486 | WFPRC-SW | Advertising and Media , Magazines, Publicity, Excerpts, and Communication including Internet | Plan | UGX | 30000000 | GOU | ODB | Lumpsum/ framework | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
487 | WFPRC-SW | supply of Fuel Oils and Lubricants | Plan | UGX | 50000000 | GOU | ODB | lumpsum/ framework | 2019-08-21 | 23rd-Aug-19 | 27th-Aug-2019 | 17th-Sept-2019 | 24th-Sept-2019
Actual
488 | PPD | Computer supplies and Information Technology (IT) | Plan | UGX | 35000000 | GOU | RFQ | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
489 | PPD | Welfare and Entertainment | Plan | UGX | 46000000 | GOU | RFQ | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
490 | PPD | Printing, Stationery, Photocopying and Binding -Sector Ministerial Policy Statements and Budget Framework paper | Plan | UGX | 50000000 | GOU | RFQ | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
491 | PPD | Small Office Equipment | Plan | UGX | 25000000 | GOU | RFQ | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
492 | PPD | Maintenance - Vehicles | Plan | UGX | 10000000 | GOU | RFQ | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
493 | PPD | workshops and Seminars Quarterly review and Half annual performance review conferences | Plan | UGX | 85000000 | GOU | RFP | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
494 | PPD | Purchase of a photocopier, 03 power stabilisers | Plan | UGX | 25000000 | GOU | RFQ | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
495 | PPD | Purchase of 03 printers | Plan | UGX | 6000000 | GOU | RFQ | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
496 | PPD | Purchase of 5 laptops | Plan | UGX | 12500000 | GOU | RFQ | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
497 | PPD | Purchase of three Water despensers | Plan | UGX | 4000000 | GOU | MICRO | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
498 | PPD | Purchase of 2 cubin files | Plan | UGX | 5000000 | GOU | MICRO | Lumpsum | 2019-07-15 | 2019-07-20 | 2019-07-25 | 2019-07-30 | 2019-08-04
Actual
499 | WFP | Design and construction of 9 valley tanks for Nakapiririt/ Amudat, Moroto and Kotido districts under Drought Resilience in the Karamoja Sub-region project. | Plan | UGX | 3000000000 | KFW/ GoU | ODB | Lumpsum | 2019-10-31 | 2019-11-30 | 2019-12-30 | 2020-01-29 | 2020-02-28
|  |  | Name | [5 empty] | Name
|  | Prepared By | Signature: |  |  |  |  | Approved By | Signature:
|  |  | Designation: | [5 empty] | Designation:
|  |  | Date: | [5 empty] | Date:
Formulas:
Bid Closing-Opening = [INVITATION AND AWARD OF BIDS]+30
Approval Evaluation Report = [Bid Closing-Opening]+30
Award Notification Date = [Approval Evaluation Report]+30
INVITATION AND AWARD OF BIDS = [Contract Type]+10
INVITATION AND AWARD OF BIDS = '[16]GW&Non-conultancy -internal use'!N23
Contract Signing Date = [Award Notification Date]+20